## MONITORING
ACTIVITY |  | PAKET 1 (UNSRAT & UNG) | [13 empty] | PAKET 2 (UNTAN & UNLAM) | [13 empty] | PAKET 3 (UNY & UNESA) | [13 empty] | PAKET 4 (UNSYIAH) | [9 empty] | EQC GABUNGAN |  | FAC |  | PMU EXPERTS
|  | DEDC P1 PT. PATROON ARSINDO |  | PMSC P1 PT. GRIKSA CIPTA |  | EQC |  | Civil Work (CW) UNSRAT |  | Equipment UNSRAT |  | CW UNG |  | Equipment UNG |  | DEDC P2 JV: PT. ARTEFAK ARKINDO - PT. DISIPLAN |  | PMSC P2 PT. DETA DECON |  | EQC |  | CW UNTAN |  | Equipment UNTAN |  | CW UNLAM |  | Equipment UNLAM |  | DEDC P3 JV: PT. WIDHA - PT. POLA DATA CONSULTANT |  | PMSC P3 JV: PT. CAKRA MANGGILINGAN JAYA - PT. ADHICIPTA ENGINEERING CONSULTAN |  | EQC |  | CW UNESA |  | Equipment UNY |  | CW UNY |  | Equipment UNESA |  | DEDC P4 PT. SUPERNOVA JAYA MANDIRI |  | PMSC P4 PT. KOGAS DRIYAP KONSULTAN |  | EQC P4 |  | CW UNSYIAH |  | Equipment UNSYIAH | [5 empty] | PROCUREMENT SPECIALIST (PS) SUTARNO |  | FINANCIAL MANAGEMENT SPECIALIST (FMS) WADIYO |  | INFORMATION AND COMMUNICATION TECHNOLOGY (ICTS) AVINANTA TARIGAN |  |  |  | CIVIL ENGINEERING SPECIALIST (CES)
CONSULTANT | WORKS | [60 empty] | IKLAN I |  | IKLAN II |  | IKLAN I |  | IKLAN II | IKLAN III | IKLAN IV | IKLAN V
EXPRESSION OF INTEREST (EoI) / SHORT LISTING (ShL) | GENERAL PROCUREMENT NOTICE (GPN)
Request NOL PQ Document / TOR IC | Submission to IDB/SFD | 2014-09-27 |  | 2014-09-27 |  |  |  | 2015-03-23 |  |  |  | 2015-03-23 |  |  |  | 2014-09-27 |  | 2014-09-27 |  |  |  | 2015-03-23 |  |  |  | 2015-03-23 |  |  |  | 2014-09-27 |  | 2014-09-27 |  |  |  | 2015-03-23 |  |  |  | 2015-03-23 | [9 empty] | 2015-04-30 |  |  |  | 2016-04-25 | 261/B/IDB/PMU-7in1/2016 | 2016-04-25 | 261/B/IDB/PMU-7in1/2016 | 2014-06-04 |  | 2014-06-04 |  | 2014-06-04 |  |  |  | 2014-06-04 |  |  |  |  | Request Re-Procure | 2016-02-25 | 128/B/IDB/PMU/2016
Request NOL PQ Document / TOR IC | [53 empty] | 2016-05-10 | 262/B/IDB/PMU-7in1/2016 | 2016-05-10 | 262/B/IDB/PMU-7in1/2016
Comment IDB/SFD - 1 | [53 empty] | 27 Mei 2016 |  | 27 Mei 2016
Response PMU | [53 empty] | 2016-05-30 |  | 6 Juni 2016
Comment IDB/SFD - 2 | [53 empty] | 2016-06-08 |  | 2016-06-08
Response PMU | [53 empty] | 24 Juni 2016 |  | 24 Juni 2016
Comment IDB/SFD - 3 | [53 empty] | 1 Juli 2016 |  | 1 Juli 2016
Response PMU | [53 empty] | 15 Juli 2016 |  | 15 Juli 2016
Comment IDB/SFD - 4 | [53 empty] | 19 Juli 2016 |  | 19 Juli 2016
Response PMU | [53 empty] | 4 Agustus 2016 |  | 4 Agustus 2016
Comment IDB/SFD - 5 | [53 empty] | 9 Agustus 2016 |  | 9 Agustus 2016
Response PMU | [53 empty] | 10 Agustus 2016 |  | 10 Agustus 2016
Comment IDB/SFD - 6 | [53 empty] | 29 Agustus 2016 |  | 29 Agustus 2016
Response PMU | [53 empty] | 30 Agustus 2016 |  | 30 Agustus 2016
NOL PQ Document / TOR IC | NOL GPN | 2014-09-30 | HDE/STC/1374 | 2014-09-30 | HDE/STC/1374 |  |  | tidak ada, langsung publish di web IDB |  |  |  | tidak ada, langsung publish di web IDB |  |  |  | 2014-09-30 | HDE/STC/1374 | 2014-09-30 | HDE/STC/1374 |  |  | tidak ada, langsung publish di web IDB |  |  |  | tidak ada, langsung publish di web IDB |  |  |  | 2014-09-30 | HDE/STC/1374 | 2014-09-30 | HDE/STC/1374 |  |  | tidak ada, langsung publish di web IDB |  |  |  | tidak ada, langsung publish di web IDB | [9 empty] | 2016-01-11 | 2016/8966 |  |  | - |  | - |  | 2014-07-17 | HDE/STC/1069 | 2014-07-17 | HDE/STC/1069 | 2014-07-17 | HDE/STC/1069 |  |  | 2014-07-17 |  |  |  |  | NOL Re-Procure | 2016-03-09 | HDE/EDU/277
Request Revised NOL PQ Document / TOR IC | Publish GPN - IDB/SFD Web | - |  | - |  |  |  | 2015-04-02 |  |  |  | 2015-04-02 |  |  |  | - |  | - |  |  |  | 2015-04-02 |  |  |  | 2015-04-02 |  |  |  | - |  | - |  |  |  | 2015-04-02 |  |  |  | 2015-04-02 | [9 empty] | 24 Februari 2015 |  |  |  | - |  | - | [9 empty] | 2015-06-04
NOL revised PQ Document / TOR IC | Publish GPN - Embassy | - |  | - |  |  |  | 2015-05-04 |  |  |  | 2015-05-04 |  |  |  | - |  | - |  |  |  | 2015-05-04 |  |  |  | 2015-05-04 |  |  |  | - |  | - |  |  |  | 2015-05-04 |  |  |  | 2015-05-04 | [9 empty] | 2016-02-09 |  |  |  | - |  | - | [9 empty] | 2 Juli 2015
Publish ShL (advertisement) - 1 | Workshop Civil Work | 2014-10-15 | 001/PP.IDB.DEDC/X/2014 | 2015-01-19 |  |  |  | 23-25 April 2015 | [7 empty] | 2014-10-29 | 003/PP.IDB.DEDC/X/2014 | 2015-02-03 | [11 empty] | 12 November 2014 |  | 2015-02-16 | [11 empty] | 2014-10-24 | 002/PP.SFD.DEDC/X/2014 | 2015-02-25 | [7 empty] | 2016-09-19 | 001/PP.IDB.EQC/IX/2016 | 2016-09-22 | 001/PP.IDB.FAC/IX/2016 | 2014-10-07 | 01/IDB/IC/X/2014 | 2014-10-07 | 01/IDB/IC/X/2014 | 2014-10-07 | 01/IDB/IC/X/2014 | 2014-10-31 | 02/IDB/IC/X/2014 | 2015-01-15
Publish ShL (advertisement) - 2 |  | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | - | [13 empty] | 2015-04-01 | [19 empty] | 2015-02-09
Publish ShL (advertisement) - 3 |  | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | - | [33 empty] | 2015-03-12
Publish ShL (advertisement) - 4 |  | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | - | [33 empty] | 8 Agusutus 2015
Publish ShL (advertisement) - 5 |  | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | - | [39 empty] | 0 | 08/IDB/IC/III/2016
Submission Document ShL |  | 18 November 2014 |  | 2015-02-18 | [11 empty] | 2014-12-02 |  | 2015-03-04 | [11 empty] | 2014-12-16 |  | 2015-03-18 | [11 empty] | 27 November 2014 |  | 6 Mei 2015 | [25 empty] | 30 Maret - 20 April
MoM Submit & Open ShL Document |  | 2014-11-18 | 450/BA.DEDC/IDB/XI/2014 | 2015-02-18 | 783/BA.DEDC/IDB/II/2015 |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2014-12-02 | 495/BA.DEDC/IDB/XII/2014 | 2015-03-04 | 830/BA.PMSC/IDB/III/2015 | [12 empty] | 2015-03-18 | 882/BA.PMSC/IDB/III/2015 | [10 empty] | 2014-11-27 | 482/BA.DEDC/IDB/XI/2014 | 2015-08-25 | 1436/BA.PMSC/IDB/VIII/2015 | [10 empty] | 2014-10-28 | 388/BA.IC/IDB/XI/2014 | 2014-10-28 | 388/BA.IC/IDB/XI/2014 | 2014-10-28 | 388/BA.IC/IDB/XI/2014 | 2014-11-18 | 451/BA.IC/IDB/XI/2014 | [6 empty] | 2016-05-03 | 272/BA.IC/IDB/V/2016
[8 empty] | 2015-12-07 | HDE/EDU/1913 |  |  | 2015-12-07 | HDE/EDU/1913 | [44 empty] | 2014-10-28 | 389/BA.IC/IDB/XI/2014 | 2014-10-28 | 389/BA.IC/IDB/XI/2014 | 2014-10-28 | 389/BA.IC/IDB/XI/2014 | 2014-11-18 | 452/BA.IC/IDB/XI/2014
MoM Evaluation ShL Document |  | 2014-12-06 | 523/BA.IC/IDB/XII/2014 | 2015-02-21 | 790/BA.DEDC/IDB/II/2015 |  |  | 2015-12-21 |  |  |  | 2015-12-21 |  |  |  | 2014-12-06 | 510/BA.IC/IDB/XII/2014 | 2015-03-04 | 834/BA.PMSC/IDB/III/2015 | [12 empty] | 2015-03-18 | 883/BA.PMSC/IDB/III/2015 | [10 empty] | 2014-12-06 | 509/BA.IC/IDB/XII/2014 | [12 empty] | 2014-11-19 | 457/BA.IC/IDB/XI/2014 | 2014-11-19 | 457/BA.IC/IDB/XI/2014 |  |  | 2014-11-28 | 486/BA.IC/IDB/XI/2014 | [6 empty] | 2016-05-03 | 278/BA.IC/IDB/V/2016
[8 empty] | 2015-12-21 |  |  |  | 2015-12-21
[8 empty] | 2015-12-21 |  |  |  | 2015-12-21
[8 empty] | 2015-12-24 |  |  |  | 2015-12-24
Request NOL ShL Report |  | 2014-12-12 |  | 2015-02-23 |  |  |  | 2015-12-28 |  |  |  | 2015-12-28 |  |  |  | 2015-12-18 |  | 2015-03-09 | [11 empty] | 2015-12-29 |  | 2015-03-28 | [11 empty] | 2014-12-18 |  | 2015-09-03 | [11 empty] | 2014-11-20 |  | 2014-11-20 |  |  |  | 2014-12-03 | 499/E3.IDB/PMU/14 | [6 empty] | 2016-05-13 | 298/B/IDB/PMU-7in1/2016
Comment IDB/SFD |  | - |  | - |  |  |  | 2015-12-22 | 1834./E3-IDB/PMU/2015 |  |  | 2015-12-22 | 1834./E3-IDB/PMU/2015 |  |  | - |  | - | [11 empty] | - |  | - | [11 empty] | -
Respond PMU |  | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | - | [11 empty] | -
NOL ShL Report |  | 2014-12-22 | HDE/EDU/1782 | 2015-03-12 | HDE/EDU/394 | [10 empty] | 2015-02-08 | HDE/EDU/202 | 2015-04-14 | HDE/EDU/605 | [10 empty] | 2015-01-18 |  | 2015-04-09 | HDE/EDU/575 | [10 empty] | 2015-01-13 | OD-2015/7823 | 2015-09-03 | 2015/28898 | [10 empty] | 2014-12-04 | HDE/EDU/1664 | 2014-12-04 | HDE/EDU/1664 |  |  | 2015-01-13 | HDE/EDU/61 | [6 empty] | 2016-06-30 | HDE/EDU/831
Respond PMU (status Kogas) |  | - |  | 2015-04-10 | [11 empty] | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | -
Comment IDB (to evaluate Kogas) |  | - |  | 2015-04-11 | [11 empty] | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | -
Respond PMU (evaluate result) |  | - |  | 2015-04-14 | [11 empty] | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | -
Comment IDB/SFD (PT Kogas) |  | - |  | 2015-05-24 | [11 empty] | - |  | - | [11 empty] | - |  | - | [11 empty] | - |  | -
Announcement ShL (web Dikti/Belmawa) |  | 2014-12-30 |  | 2015-05-28 | [11 empty] | 2015-02-10 | 007/PP.DEDC.IDB.PMU/II/2015 | 2015-04-30 | [11 empty] | 2015-01-22 |  | 2015-04-30 | [11 empty] | 2015-02-03 | 007/PP.DEDC.SFD.PMU/I/2015 | 2015-09-14 | [17 empty] | 2015-01-14 | 05/IDB/IC/I/2015
REQUEST FOR PROPOSAL (RfP) | SPECIFIC PROCUREMENT NOTICE (SPN)
Submission Request NOL RfP | Submission to IDB/SFD | 2014-10-01 |  | 2015-02-10 | [11 empty] | 2014-10-15 |  | 2015-02-23 |  |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 1 November 2014 |  | 2015-02-23 |  |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2014-10-22 |  | 4 March 2015 |  | 2016-07-28 | 521/B/SFD/PMU-7in1/2016 |  |  |  |  | 24 Juni 2016 |  | 24 Juni 2016
Comment IDB/SFD - 1 | NOL SPN | - |  | 2015-02-16 | [11 empty] | 10 November 2015 |  | 2015-03-16 |  |  |  | 2015-12-07 | HDE/EDU/1913 |  |  | 2015-12-07 | HDE/EDU/1913 |  |  | 10 November 2014 |  | 2015-03-16 |  |  |  | 2015-12-07 | HDE/EDU/1913 |  |  | 2015-12-07 | HDE/EDU/1913 |  |  | - |  | 15 March 2015 |  |  |  | 2016-01-11 | 2016/8966 |  |  | 1 Juli 2016 |  | 1 Juli 2016
Respond PMU | Publish SPN (Invitation for PQ) - IDB/SFD Web | - |  | 2015-02-17 | [11 empty] | 14 November 2015 |  | 2015-03-28 |  |  |  | 2015-12-21 |  |  |  | 2015-12-21 | www.isdb.org |  |  | 11 Desemmber 2014 |  | 2015-04-28 |  |  |  | 2015-12-21 | www.isdb.org |  |  | 2015-12-21 |  |  |  | - | [9 empty] | 15 Juli 2016 |  | 15 Juli 2016
Comment IDB/SFD - 2 | Publish SPN - PMU - Financial Times | - |  | 2015-03-16 | [11 empty] | 2015-12-02 |  | - |  |  |  | 2015-12-21 |  |  |  | 2015-12-21 | Europe, UK, US, Asia | [8 empty] | 2015-12-21 | Europe, UK, US, Asia |  |  | 2015-12-21 |  |  |  | - | [9 empty] | 19 Juli 2016 |  | 19 Juli 2016
Respond PMU | Publish SPN - PMU - Tempo | - |  | 2015-04-28 | [11 empty] | 2015-12-02 |  | - |  |  |  | 2015-12-21 |  |  |  | 2015-12-21 | [9 empty] | 2015-12-21 |  |  |  | 2015-12-21 |  |  |  | - | [5 empty] | 2016-04-14 |  |  |  | 4 Agustus 2016 |  | 4 Agustus 2016
Comment IDB/SFD - 3 | [53 empty] | 9 Agustus 2016 |  | 9 Agustus 2016
Respond PMU | [53 empty] | 10 Agustus 2016 |  | 10 Agustus 2016
Comment IDB/SFD - 4 | [53 empty] | 29 Agustus 2016 |  | 29 Agustus 2016
Respond PMU | [53 empty] | 30 Agustus 2016 |  | 30 Agustus 2016
Comment IDB/SFD - 5 | [53 empty] | 2016-09-05
Respond PMU | [53 empty] | 2016-09-08
NOL RfP | Publish SPN - Local/PIU - University web | 2014-10-30 | HDE/STC/1500 | 2015-04-28 | HDE/STC/678 | [10 empty] | 2014-12-04 | HDE/STC/1668 | 2015-04-28 | HDE/STC/678 |  |  | 2015-12-24 |  |  |  | - |  |  |  | 2014-12-11 |  | 2015-04-28 | HDE/STC/678 |  |  | 2015-12-28 | www.unesa.ac.id ; www.lpse.unesa.ac.id |  |  | 2015-12-28 |  |  |  | 19 November 2014 | TD-2014/2325 | 2015-04-15 | OD-2015/16887 | 11 Oktober 2016 | 2016/977 |  |  |  |  | 2016-09-08 | HDE/EDU/1122 | 2016-09-07 | HDE/EDU/1113
Comment IDB - After NOL | Publish SPN - Local/PIU - Local Newspaper | - |  | 2015-05-27 | [11 empty] | - |  | 2015-05-27 |  |  |  | 2015-12-28 |  |  |  | 2015-12-24 | Banjarmasin Post |  |  |  |  | 2015-05-27 |  |  |  | 2015-12-28 |  |  |  | 2015-12-28 |  |  |  | -
Respond PMU - After NOL | Publish SPN - Embassy | - |  | 2015-05-28 | [11 empty] | - |  | 2015-05-28 |  |  |  | 2015-12-22 | 1834./E3-IDB/PMU/2015 |  |  | 2015-12-22 | 1834./E3-IDB/PMU/2015 |  |  |  |  | 2015-05-28 |  |  |  | 2015-12-22 | 1834./E3-IDB/PMU/2015 |  |  | 2015-12-22 | 1834./E3-IDB/PMU/2015 |  |  | -
Invitation Submission RfP |  | 2015-01-05 |  | 1 June 2015 | [11 empty] | 2015-02-16 |  | 2015-05-11 | [11 empty] | 2015-01-26 |  | 2015-05-15 | [11 empty] | 2015-02-09
Aanwijzing |  | 2015-01-19 |  | 2015-06-15 | [11 empty] | 2015-03-02 |  | 2015-05-25 | [11 empty] | 2015-02-09 |  | 2015-06-01 | 1163/UND/E3-IDB/2015 | [10 empty] | 2015-02-23
MoM Aanwijzing |  |  |  | 2015-06-15 | 1216/BA.PMSC/IDB/VI/2015 | [12 empty] | 2015-05-25 | 1149/BA.PMSC/IDB/V/2015 | [12 empty] | 2015-06-01 | 1175/BA.PMSC/IDB/VI/2015
TECHNICAL EVALUATION (TER) | PRE-QUALIFICATION (PQ) DOCUMENT
Submission T&F Proposal | Submission to IDB/SFD | 2015-02-16 |  | 2015-07-23 |  |  |  | 2015-06-17 | 1226/E3.IDB/PMU/2015 |  |  | 2015-06-17 | 1226/E3.IDB/PMU/2015 |  |  | 2015-03-30 |  | 2015-06-22 |  |  |  | 2015-09-11 | 1479/E3.IDB/PMU/15 |  |  | 2015-09-11 | 1479/E3.IDB/PMU/15 |  |  | 2015-03-09 |  | 2015-06-26 |  |  |  | 2015-09-11 | 1479/E3.IDB/PMU/15 |  |  | 2015-09-11 | 1479/E3.IDB/PMU/15 |  |  | 2015-03-23 | [5 empty] | 2016-02-15 | 102/B/SFD/PMU-7in1/2016
Penawaran Perusahaan (s/d tgl ..) | Comment IDB/SFD - 1 | [6 empty] | 2015-07-28 |  |  |  | 2015-07-28 | [31 empty] | 2015-06-24
Perpanjangan Penawaran Perusahaan-1 (s/d tgl ..) | Respond PMU/PIU - 1 | [6 empty] | 2015-09-04 | - |  |  | 2015-09-04 | - | [30 empty] | 2015-09-19
Perpanjangan Penawaran Perusahaan-2 (s/d tgl ..) | Respond PMU/PIU - 2 | [6 empty] | 2015-11-11 | 1721/E3.IDB/PMU/15 |  |  | 2015-11-11 | 1721/E3.IDB/PMU/15 | [8 empty] | 2015-11-11 | 1721/E3.IDB/PMU/15 |  |  | 2015-11-11 | 1721/E3.IDB/PMU/15 | [8 empty] | 2015-11-11 | 1721/E3.IDB/PMU/15 |  |  | 2015-11-11 | 1721/E3.IDB/PMU/15 |  |  | 2015-12-19
Perpanjangan Penawaran Perusahaan-3 (s/d tgl ..) | Comment IDB/SFD - 2 | [6 empty] | 2015-11-17 | - |  |  | 2015-11-17 | - | [8 empty] | 2015-11-17 | - |  |  | 2015-11-17 | - | [8 empty] | 2015-11-17 | - |  |  | 2015-11-17 | - |  |  | 2016-03-18
MoM Submit & Open Technical Document | Comment IDB/SFD - 3 | 2015-02-16 | 773/BA.DEDC/IDB/II/2015 | 2015-07-23 | 1326/BA.PMSC/IDB/VII/2015 | [10 empty] | 2015-03-30 | 914/BA.DEDC/IDB/III/2015 | 2015-06-22 | 1242/BA.PMSC/IDB/VI/2015 | [12 empty] | 2015-06-26 | 1267/BA.PMSC/IDB/VI/2015 | [10 empty] | 2015-03-23 | 801/BA.DEDC/SFD/III/2015 | 2015-10-29 | 1678/BA.PMSC/SFD/X/2015
MoM Evaluation Technical Document | Respond PMU/PIU - 3 | 2015-02-16 | 774/BA.DEDC/IDB/II/2015 |  |  |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-04-27 | 1005/BA.IC/IDB/IV/2015 |  |  |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 | [8 empty] | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-11-26 | 1764/E3.IDB/PMU/15 |  |  | 2015-04-06 | 840/BA.DEDC/SFD/IV/2015 | 2015-10-31 | 1684/BA.PMSC/SFD/X/2015
TER | NOL PQD | 2015-03-16 | [5 empty] | 2015-12-07 | HDE/EDU/1913 |  |  | 2015-12-07 | HDE/EDU/1913 |  |  | 2015-05-30 | [5 empty] | 2015-12-07 | HDE/EDU/1913 |  |  | 2015-12-07 | HDE/EDU/1913 | [8 empty] | 2015-12-07 | HDE/EDU/1913 |  |  | 2015-12-07 | HDE/EDU/1913 | [8 empty] | 2016-02-22 | 2016/13739
Request NOL TER 1st | Invitation for PQ | 2015-03-18 | 879/E3.IDB/PMU/15 | 2015-08-04 |  |  |  | 22 Desember 2015 - 25 Februari 2016 |  |  |  | 2015-12-24 |  |  |  | 2015-05-30 | 1174/E3.IDB/PMU/15 | 2015-08-04 |  |  |  | 2015-12-24 |  |  |  | 24 Desember 2015 - 7 Maret 2016 |  |  |  | 2015-04-28 |  | 2015-08-04 |  |  |  | 2015-12-28 | [7 empty] | 2015-04-26 |  | 2015-11-12 |  |  |  | 2016-04-12 | [15 empty] | 16 May 2015
Request NOL TER 2nd | Registration & Obtaining of PQD | - |  | - |  |  |  | 22 Desember 2015 - 25 Februari 2016 |  |  |  | 24 Desember 2015 - 26 Februari 2016 |  |  |  | - |  | - |  |  |  | 24 Desember 2015 - 3 Maret 2016 |  |  |  | 24 Desember 2015 - 7 Maret 2016 |  |  |  | - |  | - |  |  |  | 28 Desember 2015 - 10 Maret 2016 |  |  |  | 28 Desember 2015 - 14 Maret 2016 |  |  |  | - |  | - |  |  |  | 2016-04-14 | [15 empty] | 2015-09-09
Comment IDB/SFD | Submission of Applications | 2015-03-26 |  | 19 Agustus 2015 |  |  |  | 22 Desember 2015 |  |  |  | s/d 29 Februari 2016 |  |  |  | - |  | 19 Agustus 2015 |  |  |  | 24 Desember 2015 - 3 Maret 2016 |  |  |  | 28 Desember 2015 - 7 Maret 2016 |  |  |  | - |  | 19 Agustus 2015 |  |  |  | 28 Desember 2015 - 10 Maret 2016 |  |  |  | 28 Desember 2015 - 14 Maret 2016 |  |  |  | - |  | 2015-11-24 |  |  |  | 14 April 2016 - 13 Juni 2016
Response PMU - 1 | Pre-Application Meeting (Aaanwijzing) | 2015-04-16 |  | 2015-09-04 |  |  |  | 2016-01-07 |  |  |  | 2016-01-11 |  |  |  | - |  | 2015-09-04 |  |  |  | 2016-01-14 |  |  |  | 2016-01-18 |  |  |  | - |  | 2015-09-04 |  |  |  | 2016-01-21 |  |  |  | 2016-01-25 |  |  |  | - |  | 2015-11-26 |  |  |  | .
Comment IDB/SFD | Deadline for PQ Submission | [6 empty] | 2016-02-25 |  |  |  | 2016-02-29 |  |  |  | - | [5 empty] | 2016-03-03 |  |  |  | 2016-03-07 |  |  |  | - | [5 empty] | 2016-03-10 |  |  |  | 2016-03-14 |  |  |  | -
Respond PMU | PQ Application Opening | [6 empty] | 2016-02-25 |  |  |  | 2016-02-29 |  |  |  | - | [5 empty] | 2016-03-03 |  |  |  | 2016-03-07 |  |  |  | - | [5 empty] | 2016-03-10 |  |  |  | 2016-03-14 |  |  |  | -
Comment IDB/SFD | Evaluation for PQ | - |  | 2015-09-18 |  |  |  | 17 Maret 2016 |  |  |  | 2016-03-07 |  |  |  | - |  | 2015-09-18 |  |  |  | 4 Maret - 17 Maret 2016 |  |  |  | 21 Maret 2016 |  |  |  | - |  | 2015-09-18 |  |  |  | 10-31 Maret 2016 |  |  |  | 14 Maret - 1 April 2016 |  |  |  | - |  | 13 Desember 2015 |  |  |  | 14 Juni 2016 - 12 Agustus 2016
Response PMU - 2 | PQ Evaluation Report | - |  | 2015-09-29 |  |  |  | 2016-03-10 |  |  |  | 2016-03-14 |  |  |  | - |  | 2015-09-29 |  |  |  | 2016-03-17 |  |  |  | 2016-03-21 |  |  |  | - |  | 2015-09-29 |  |  |  | 2016-03-24 | [7 empty] | - |  | -
Comment IDB/SFD | Submission PQD Evaluation Report to IDB/SFD | - |  | 21 Oktober 2015 |  |  |  | 4 Mei 2016 | 274/B/IDB/PMU-7IN1/2016 |  |  | 4 Mei 2016 | 274/B/IDB/PMU-7IN1/2016 |  |  | - |  | 21 Oktober 2015 |  |  |  | 4 Mei 2016 | 274/B/IDB/PMU-7IN1/2016 |  |  | 4 Mei 2016 | 274/B/IDB/PMU-7IN1/2016 |  |  | - |  | 21 Oktober 2015 |  |  |  | 4 Mei 2016 | 274/B/IDB/PMU-7IN1/2016 |  |  | 4 Mei 2016 | 274/B/IDB/PMU-7IN1/2016 |  |  | - |  | - |  |  |  | 2016-09-08 | 652/B/SFD/PMU-7in1/2016
| Comment IDB/SFD - 1 | [6 empty] | 3 dan 6 Juni 2016 |  |  |  | 3 dan 6 Juni 2016 | [9 empty] | 3 dan 6 Juni 2016 |  |  |  | 3 dan 6 Juni 2016 | [9 empty] | 3 dan 6 Juni 2016 |  |  |  | 3 dan 6 Juni 2016
Respond PMU/PIU - 1
| Comment IDB/SFD - 2 | [6 empty] | 2016-06-21 |  |  |  | 2016-06-21 | [9 empty] | 2016-06-21 |  |  |  | 2016-06-21 | [9 empty] | 2016-06-21 |  |  |  | 2016-06-21
| Respond PMU/PIU - 2 | [6 empty] | 12 Agusutus 2016 |  |  |  | 12 Agusutus 2016 | [9 empty] | 12 Agusutus 2016 |  |  |  | 12 Agusutus 2016 | [9 empty] | 12 Agusutus 2016 |  |  |  | 12 Agusutus 2016
| Comment IDB/SFD - 3 | [6 empty] | 31 Agustus 2016 | 658/B/IDB/PMU/2016 |  |  | 31 Agustus 2016 | 658/B/IDB/PMU/2016 | [8 empty] | 31 Agustus 2016 | 658/B/IDB/PMU/2016 |  |  | 31 Agustus 2016 | 658/B/IDB/PMU/2016 | [8 empty] | 31 Agustus 2016 | 658/B/IDB/PMU/2016 |  |  | 31 Agustus 2016 | 658/B/IDB/PMU/2016
| Respond PMU/PIU - 3 | [6 empty] | 2016-09-29
Response PMU - 3 | NOL of Evaluation PQ | - |  | 2015-11-02 |  |  |  | 2016-09-29 | HDE/EDU/1182 |  |  | 2016-09-29 | HDE/EDU/1182 |  |  | - |  | 2015-11-02 |  |  |  | 2016-09-29 | HDE/EDU/1182 |  |  | 2016-09-29 | HDE/EDU/1182 |  |  | - |  | 2015-11-02 |  |  |  | 2016-09-29 | HDE/EDU/1182 |  |  | 2016-09-29 | HDE/EDU/1182 |  |  | - |  | -
Comment IDB/SFD | Publication of PQ Contractors | - |  | 7 Januari 2015 | [7 empty] | 2016-03-31 |  |  |  | - |  | 7 Januari 2015 |  |  |  | 2016-04-04 |  |  |  | 2016-04-07 |  |  |  | - |  | 7 Januari 2015 |  |  |  | 2016-04-11 |  |  |  | 2016-04-11 |  |  |  | - |  | -
Response PMU - 4 | Invitation for Bidding | - |  | 20 Januari 2015 | [7 empty] | July |  |  |  | - |  | 20 Januari 2015 |  |  |  | July |  |  |  | July |  |  |  | - |  | 20 Januari 2015 |  |  |  | July |  |  |  | July |  |  |  | - |  | -
NOL TER |  | 2015-05-10 | HDE/765 | 26 Januari 2016 | HDE/EDU/93 | [10 empty] | 2015-06-24 | HDE/STC/1023 | 26 Januari 2016 | HDE/EDU/93 | [10 empty] | 2015-06-09 |  | 26 Januari 2016 | HDE/EDU/93 | [10 empty] | 2015-06-01 | 2015/21132 | 2016-01-10 | 2016/882
[44 empty] | 2015-04-30 | 2015/18318
Pengumuman hasil TER (web Dikti/Belmawa) | [31 empty] | 2016-02-29 | 130/PP.PMSC.IDB.PMU/II/2016 | [10 empty] | 2015-06-10 | 010/PP.DEDC.SFD.PMU/VI/2015
COMBINE EVALUATION (CER) | BID DOCUMENT
Invitation Open Financial Proposal | Submission Bidding Document, RKS, BoQ, dan Gambar to IDB | 2015-06-25 |  | 26 Januari 2016 | 060.1/PD/B/IDB/2016 |  |  | 25 Agustus 2016 | 615/B/IDB/PMU/2016 |  |  | 25 Agustus 2016 | 615/B/IDB/PMU/2016 |  |  | 2015-07-01 |  | 27 Januari 2016 | 064.1/PD/B/IDB/2016 |  |  | 25 Agustus 2016 | 615/B/IDB/PMU/2016 |  |  | 29 Agustus 2016 | 615/B/IDB/PMU/2016 |  |  | 2015-06-19 |  | 27 Januari 2016 | 067/PD/B/IDB/2016 |  |  | 23 Agusutus 2016 | 615/B/IDB/PMU/2016 |  |  | 23 Agusutus 2016 | 615/B/IDB/PMU/2016 |  |  | 2015-06-25 |  | 15 Januari 2016 | 035.1/PD/B-SFD/2016 |  |  | 2016-10-11 | 760/B/SFD/PMU-7in1/2016
Open Financial Proposal | Comment IDB/SFD - 1 | 2015-06-30 |  | 29 Januari 2016 |  |  |  | 2016-09-21 |  |  |  | 2016-09-21 |  |  |  | 2015-07-04 |  | 1 Februari 2016 |  |  |  | 2016-09-21 |  |  |  | 2016-09-21 |  |  |  | 2015-06-23 |  | 2 Februari 2016 |  |  |  | 2016-09-21 |  |  |  | 2016-09-21 |  |  |  | 2015-06-29 |  | 2016-01-22
MoM Opening Financial Document | Respond PMU/PIU - 1 | 2015-06-30 | 1283/BA.DEDC/IDB/VI/2015 | 29 Januari 2016 | 073/BA.PMSC/IDB/I/2016 |  |  | 2016-09-23 |  |  |  | 2016-09-22 |  |  |  | 2015-07-04 | 1292/BA.DEDC/IDB/VII/2015 | 1 Februari 2016 | 077/BA.PMSC/IDB/II/2016 |  |  | 2016-09-22 |  |  |  | 2016-09-22 | [5 empty] | 2016-02-02 | 079/BA.PMSC/IDB/II/2016 |  |  | 2016-09-22 |  |  |  | 2016-09-22 |  |  |  | 2015-06-29 | 1282/BA.DEDC/SFD/VI/2015 | 2016-01-22 | 050/BA.PMSC/SFD/I/2016
CER | Respond PMU/PIU - 2 | [6 empty] | 2016-09-26 |  |  |  | 2016-09-26 |  |  |  | 2015-07-29 | [5 empty] | 2016-09-26 |  |  |  | 2016-09-26 | [9 empty] | 2016-09-26 |  |  |  | 2016-09-26
Request NOL Evaluation Report TP & FP | NOL Bidding Document | 2015-07-30 |  | 5 Februari 2016 |  |  |  | 2016-10-10 | HDE/EDU/1227 |  |  | 2016-10-10 | HDE/EDU/1227 |  |  | 2015-07-30 |  | 5 Februari 2016 |  |  |  | 2016-10-10 | HDE/EDU/1227 |  |  | 2016-10-10 | HDE/EDU/1227 |  |  | 2015-07-30 |  | 5 Februari 2016 |  |  |  | 2016-10-10 | HDE/EDU/1227 |  |  | 2016-10-10 | HDE/EDU/1227 |  |  | 1 Agustus 2015 |  | 2016-01-27
Comment IDB/SFD |  | 5 Agustus 2015 | [13 empty] | 5 Agustus 2015
Response PMU - 1 |  | 6 Agustus 2015 | [13 empty] | 6 Agustus 2015
Pengiriman MoM Penentuan Pemenang Paket 1 dan 2 |  | 25 Agustus 2015 | [13 empty] | 25 Agustus 2015
NOL CER |  | 2015-09-29 | HDE/EDU/1548 | 2016-02-25 | HDE/EDU/224 | [10 empty] | 2015-09-29 | HDE/EDU/1548 | 2016-02-25 | HDE/EDU/224 | [10 empty] | 2015-09-29 |  | 2016-02-25 | HDE/EDU/224 | [10 empty] | 08 Oktober 2015 | 2015/30994 | 2016-02-22 | 2016/13738
Pengumuman hasil CER (web Dikti/Belmawa) |  |  |  | 2016-02-29 | 130/PP.PMSC.IDB.PMU/II/2016 | [10 empty] | 2015-10-02 | 1563/PP.DEDC.IDB.PMU/X/2015 | 2016-02-29 | 130/PP.PMSC.IDB.PMU/II/2016 | [12 empty] | 2016-02-29 | 130/PP.PMSC.IDB.PMU/II/2016 | [10 empty] | 2015-10-28 | 1677/PP.DEDC.IDB.PMU/X/2015 | 2016-03-01 | 132/PP.PMSC.SFD.PMU/II/2016
CLARIFICATION & NEGOTIATION (C&N)
Negotiation TP & FP - 1 |  | 9 Oktober 2015 |  | 14-15 Maret 2016 | 147/UND/B/PMU-7in1/2016 | [10 empty] | 10 Oktober 2015 |  | 4-5 Maret 2016 | [11 empty] | 8 Oktober 2015 |  | 7-8 Maret 2016 | [11 empty] | 2015-11-03 |  | 10-11 Maret 2016 | [11 empty] | 2014-12-12 | 518/UND/E3-IDB/14 | 20 Desember 2014 | 536/UND/E3-IDB/14 |  |  | 2015-01-23 | 640/PD/E3-IDB/15 | 13 Oktober 2015
MOM C&N - 1 |  |  |  | 2016-03-14 | 178/BA.PP.IDB.PMSC/III/2016 | [12 empty] | 2016-03-04 | 152/BA.PP.IDB.PMSC/III/2016 | [12 empty] | 2016-03-07 | 155/BA.PP.IDB.PMSC/III/2016 | [12 empty] | 2016-03-10 | 170/BA.PP.SFD.PMSC/III/2016 | [10 empty] | 2014-12-20 | 542/BA.IC/IDB/XII/2014 | 20 Desember 2014 | 543/BA.IC/IDB/XII/2014 |  |  | 2015-01-23 | 674/BA.IC/IDB/I/2015
Negotiation TP & FP - 2 |  | 16-17 Oktober 2015 |  | 2016-04-14 | 225/UND/B/PMU-7in1/2016 | [10 empty] | 16-17 Oktober 2015 |  | 2016-04-14 | 225/UND/B/PMU-7in1/2016 | [10 empty] | 23-24 Oktober 2015 |  | 2016-04-14 | 225/UND/B/PMU-7in1/2016 | [10 empty] | 14-15 November 2015 | [15 empty] | 2014-12-30 | 573/PD/E3-IDB/14 |  |  | 13 Februari 2015 | 744/PD/E3-IDB/15 | 2015-11-13
MOM C&N - 2 |  |  |  | 2016-04-14 | [13 empty] | 2016-04-14 | [13 empty] | 2016-04-14
Negotiation TP & FP - 3 |  | 20-21 Oktober 2015 | [13 empty] | 20-21 Oktober 2015
MOM C&N - 3
Report of C&N, and Draft Contract |  |  |  | 2016-04-20 | 451.1/PP.IDB.PMSC/IV/2016 | [10 empty] | 2015-11-02 | 1687/BA.PP.IDB.DEDC/XI/2015 | 2016-04-20 | 245.2/PP.IDB.PMSC/IV/2016 | [12 empty] | 2016-04-20 | 245.3/PP.IDB.PMSC/IV/2016 | [10 empty] | 2015-11-15 | 1732/BA.PP.SFD.DEDC/XI/2015 | 2016-05-26 | 354/PP.SFD.PMSC/V/2016
Submission Report of C&N, and Draft Contract |  | 2015-11-07 |  | 2016-04-22 | [11 empty] | 2015-11-07 |  | 2016-04-22 | [11 empty] | 2015-11-07 |  | 2016-04-22 | [11 empty] | 2015-11-16 | 1733/E3.SFD/PMU/15 | 2016-07-13 | 470/B/SFD/PMU-7in1/2016 | [23 empty] | 23 Agustus 2016 | 599/B/IDB/PMU/2016
Comment IDB/SFD | [70 empty] | 31 Agustus 2016
Response PMU | [70 empty] | 2016-09-02
Request Negotiation
NOL Negotiation/Award |  | 2015-12-06 |  | 22 Mei 2016 | HDE/EDU/608 | [10 empty] | 2015-12-06 | HDE/EDU/1912 | 22 Mei 2016 | HDE/EDU/608 | [10 empty] | 2015-12-06 |  | 22 Mei 2016 | HDE/EDU/608 | [10 empty] | 2016-01-14 |  | 2016-07-13 | 2016/26690 | [23 empty] | 2016-09-06 | HDE/EDU/1103
CONTRACT
Submission Draft Contract |  |  |  | 2016-04-20 | 256/B/IDB/PMU/2016 | [12 empty] | 2016-04-20 | 256/B/IDB/PMU/2016 | [12 empty] | 2016-04-20 | 256/B/IDB/PMU/2016 | [10 empty] | 2016-01-14 | [19 empty] | 2015-03-10 | 854/E3.IDB/PMU/15
Follow up Draft Contract by PMU
NOL Draft Contract |  | 2015-12-06 | HDE/EDU/1912 | 22 Mei 2016 | HDE/EDU/608 | [10 empty] | 2015-12-06 | HDE/EDU/1912 | 22 Mei 2016 | HDE/EDU/608 | [10 empty] | 2015-12-06 |  | 22 Mei 2016 | HDE/EDU/608 | [10 empty] | 2016-01-14 | 2016/9446 | 2016-07-13 | 2016/26690 | [23 empty] | 2016-09-06 | HDE/EDU/1103
Surat Permintaan Penetapan Pemenang Pengadaan Jasa |  | 2015-12-08 | 1789/PD/E3-IDB/2015 | 2016-05-23 | 331/PD/B/PMU-7in1/2016 | [10 empty] | 2015-12-08 | 1789.1/PD/E3-IDB/2015 | 2016-05-23 | 332/PD/B/PMU-7in1/2016 | [12 empty] | 2016-05-23 | 333/PD/B/PMU-7in1/2016 | [10 empty] | 2016-01-15 | 036/PD/B-SFD/2016 | 2016-07-14 | 478/PD/B/PMU-7in1/2016 | [10 empty] | 2015-02-16 | 777.2/PD/E3-IDB/2015 | 2015-02-16 | 777.1/PD/E3-IDB/2015 |  |  | 2015-03-16 | 873/PD/E3-IDB/2015
Surat Penunjukkan Penyedia Barang dan Jasa (SPPBJ) |  | 2015-12-10 | 1799/PD/E3-IDB/2015 | 2016-05-26 | 351/PD/B/PMU-7in1/2016 | [10 empty] | 2015-12-10 | 1800/PD/E3-IDB/2015 | 2016-05-26 | 352/PD/B/PMU-7in1/2016 | [12 empty] | 2016-05-26 | 353/PD/B/PMU-7in1/2016 | [10 empty] | 2016-01-18 | 039/PD/B-SFD/2016 | 2016-07-18 | 490/PD/B/PMU-7in1/2016 | [10 empty] | 2016-02-20 | 789/PD/E3-IDB/2015 | 2016-02-20 | 788/PD/E3-IDB/2015 |  |  | 2015-03-20 | 893/PD/E3-IDB/2015
Surat Perintah Mulai Kerja (SPMK) |  | 2015-12-16 | 1815/PD/E3-IDB/2015 | 2016-05-30 | 364/PD/B/PMU-7in1/2016 | [10 empty] | 2015-12-16 | 1816/PD/E3-IDB/2015 | 2016-05-30 | 365/PD/B/PMU-7in1/2016 | [12 empty] | 2016-05-30 | 366/PD/B/PMU-7in1/2016 | [10 empty] | 2016-01-25 | 053/PD/B-SFD/2016 | 2016-07-21 | 502/PD/B/PMU-7in1/2016 | [10 empty] | 2016-02-26 | 813/PD/E3-IDB/2015 | 2016-02-26 | 812/PD/E3-IDB/2015 |  |  | 2015-03-25 | 899/PD/E3-IDB/2015
Contract Award
Contract Date |  | 2015-12-16 | 004/DEDC/IDB/K/XII/2015 | 2016-05-30 | 008/PMSC/IDB/K/V/2016 | [10 empty] | 2015-12-16 | 005/DEDC/IDB/K/XII/2015 | 2016-05-30 | 009/PMSC/IDB/K/V/2016 | [10 empty] | 2015-12-16 | 006/DEDC/IDB/K/XII/2015 | 2016-05-30 | 010/PMSC/IDB/K/V/2016 | [10 empty] | 2016-01-25 | 007/DEDC.SFD/K/I/2016 | 2016-07-21 | 011/PMSC/SFD/K/VII/2016 | [10 empty] | 2015-02-27 | 002/IC/IDB/K/II/2015 | 2015-02-26 | 001/IC.IDB/K/II/2015 |  |  | 2015-03-25 | 003/IC.IDB/K/III/2015
Contract Signature Date |  | 2015-12-16 |  | 2016-05-30 | [11 empty] | 2015-12-16 |  | 2016-05-30 | [11 empty] | 2015-12-16 |  | 2016-05-30 | [11 empty] | 2016-01-25 |  | 2016-07-21 | [11 empty] | 2015-02-27 |  | 2015-02-26 |  |  |  | 2015-03-25
Submission Contract to IDB/SFD | [57 empty] | 2015-03-10 | 853/E3.IDB/PMU/15 | 2015-03-10 | 853/E3.IDB/PMU/15 |  |  | 2015-04-01 | 926/E3.IDB/PMU/15
Amendment Contract Date | [57 empty] | 2015-05-29 | 001/IC/IDB/AD/V/2015 | 2015-05-29 | 001/IC/IDB/AD/V/2015 |  |  | 2015-05-29 | 001/IC/IDB/AD/V/2015
Amendment Contract Signature | [57 empty] | 2015-05-29 |  | 2015-05-29 |  |  |  | 2015-05-29
Submission Amendment Contract | [57 empty] | 2015-06-07 | 1199/E3.IDB/PMU/15 | 2015-06-07 | 1199/E3.IDB/PMU/15 |  |  | 2015-06-07 | 1199/E3.IDB/PMU/15
IMPLEMENTATION
Start Date |  | 2015-12-16 |  | 2016-05-30 | [11 empty] | 2015-12-16 |  | 2016-05-30 | [11 empty] | 2015-12-16 |  | 2016-05-30 | [11 empty] | 2016-01-25 |  | 2016-07-21 | [11 empty] | 2015-03-02 |  | 2015-03-02 |  |  |  | 2015-04-01
End Contract Date |  | 2016-06-16 |  | berakhir pada saat kemajuan fisik pembangunan gedung yang dilaksanakan oleh kontraktor mencapai 100 (seratus) persen dan setelah dilaksanakannya Serah Terima Sementara Pekerjaan ditambah dengan masa pemeliharaan selama 1 (satu) tahun mencakup 12 (dua belas) bulan kalender dan diterimanya Sertifikat Penyelesaian Pekerjaan oleh Proyek | [11 empty] | 2016-06-16 |  | berakhir pada saat kemajuan fisik pembangunan gedung yang dilaksanakan oleh kontraktor mencapai 100 (seratus) persen dan setelah dilaksanakannya Serah Terima Sementara Pekerjaan ditambah dengan masa pemeliharaan selama 1 (satu) tahun mencakup 12 (dua belas) bulan kalender dan diterimanya Sertifikat Penyelesaian Pekerjaan oleh Proyek | [11 empty] | 2016-06-16 |  | berakhir pada saat kemajuan fisik pembangunan gedung yang dilaksanakan oleh kontraktor mencapai 100 (seratus) persen dan setelah dilaksanakannya Serah Terima Sementara Pekerjaan ditambah dengan masa pemeliharaan selama 1 (satu) tahun mencakup 12 (dua belas) bulan kalender dan diterimanya Sertifikat Penyelesaian Pekerjaan oleh Proyek | [11 empty] | 2016-07-25 | [13 empty] | 2016-12-31 |  | 2017-12-31 |  |  |  | 2017-12-31
Contract Period |  | 6 bulan | [13 empty] | 6 bulan | [13 empty] | 6 bulan | [13 empty] | 6 bulan | [13 empty] | 21 bulan |  | 33 bulan |  |  |  | 15 bulan
Estimated Cost |  |  |  | 990000 |  | 254190 |  | 16311066 |  | 4810365 |  | 19224068 |  | 4344000 |  |  |  | 1430868.5628 |  | 320000 |  | 20280984.3843 |  | 1406950.5873 |  | 25927688 |  | 4689000 |  |  |  | 1382056.34 |  | 298546 |  | 22201973 |  | 2519991.2328 |  | 19043517.8683 |  | 3245259 |  |  | 506000 | 760000 |  | 137151 |  | 24197596 |  | 4852059 |  | 254190 |  | 300000 |  |  | 200000 |  | 200000 |  |  |  | 200000 |  | 200000 | [5 empty] | 200000
Contract Amount (diluar pajak) |  |  | 4657750000 |  | 7433000000 | [11 empty] | 4562800000 |  | 9035710000 | [11 empty] | 6035109000 |  | 8510000000 | [11 empty] | 2499500000 |  | 4253490000 | [11 empty] | 755500000 |  | 1018822000 |  |  |  | 861300000 |  | 203981.5126
TERMIN 1 |  | Book 1: 1st Preliminary Report |  | 1: Inception Report | [11 empty] | Book 1: 1st Preliminary Report |  | 1: Inception Report | [11 empty] | Book 1: 1st Preliminary Report |  | 1: Inception Report | [11 empty] | Book 1: 1st Preliminary Report |  | 1: Inception Report | [11 empty] | Pembayaran Maret, April, Mei 2015 |  | Pembayaran Maret, April, Mei 2015 |  |  |  | Pembayaran April, Mei, Juni 2015
Presentasi |  | 20-21 Januari 2016 | [13 empty] | 19-20 Februari 2016 | [13 empty] | 12-13 Januari 2016 | [13 empty] | 11-12 Maret 2016 | [13 empty] | -
Approval |  | 2016-01-29 | 075/PD/B-IDB/2016 | [12 empty] | 2016-03-18 | 186/PD/B-IDB/2016 | [12 empty] | 2016-01-19 | 044/PD/B-IDB/2016 | [26 empty] | -
MOM |  | 2016-01-20 | 048/BA.PP.IDB.DEDC/I/2016 | [12 empty] | 2016-02-19 | 117/BA.PP.IDB.DEDC/II/2016 | [12 empty] | 2016-01-12 | 023/BA.PP.IDB.DEDC/I/2016 | [26 empty] | -
Report | [57 empty] | Progress Report Mar, Apr, Mei 2015 |  | Progress Report Mar, Apr, Mei 2015 |  |  |  | Progress Report Apr, Mei, Jun 2015
Payment |  | 2016-02-17 | 010/WA/IDB/PL/DEDC/II/2016 | [12 empty] | 2016-04-27 | 014/WA/IDB/PL/DEDC/IV/2016 | [12 empty] | 2016-02-17 | 009/WA/IDB/PL/DEDC/II/2016 | [26 empty] | 2015-06-03 | 004/WA/IDB/PL/IC/VI/2015 | 2015-06-03 | 008/WA/IDB/PL/IC/VI/2015 |  |  | 2015-07-02 | 012/WA/IDB/PL/IC/VII/2015
|  |  | 465775000 |  | 371650000 | [11 empty] | 456280000 |  | 451785500 | [11 empty] | 603510900 |  | 425500000 | [11 empty] | 249950000 |  | 212674500 | [11 empty] | 71250000 |  | 57000000 |  |  |  | 114000000
[59 empty] | 5153.71 |  | 4122.97 |  |  |  | 8245.93
Surat Perintah Pembukuan/Pengesahan (SP3) | [57 empty] | 2015-09-23 | 151403402000554 | 2015-09-23 | 151403402000555 |  |  | 2015-09-23 | 151403402000556
TERMIN 2 |  | Book 2: 2nd Preliminary Report Book 3: 1st Progress Report Book 4: 2nd Progress Report |  | 2: DED Evaluation Report | [11 empty] | Book 2: 2nd Preliminary Report Book 3: 1st Progress Report Book 4: 2nd Progress Report |  | 2: DED Evaluation Report | [11 empty] | Book 2: 2nd Preliminary Report Book 3: 1st Progress Report Book 4: 2nd Progress Report |  | 2: DED Evaluation Report | [11 empty] | Book 2: 2nd Preliminary Report Book 3: 1st Progress Report Book 4: 2nd Progress Report |  | 2: DED Evaluation Report | [11 empty] | Pembayaran Juni, Juli, Agsts 2015 |  | Pembayaran Juni, Juli, Agsts 2015 |  |  |  | Pembayaran Juli, Agsts, Sep 2015
Presentasi |  | 16-17 Maret 2016 | [13 empty] | 18-19 Maret 2016 | [13 empty] | 22-23 Maret 2016
|  | 10-11 Mei 2016 | [13 empty] | 20-21 Mei 2016 | [13 empty] | 28-29 Mei 2016
Approval |  | 2016-06-14 | Book 2: 412/PD/B-IDB/2016 | [13 empty] | Book 2: | [12 empty] | 2016-05-28 | Book 2: 360/PD/B-IDB/2016
|  | 2016-06-14 | Book 3: 413/PD/B-IDB/2016 | [13 empty] | Book 3: | [12 empty] | 2016-05-28 | Book 3: 361/PD/B-IDB/2016
|  | 2016-06-14 | Book 4: 414/PD/B-IDB/2016 | [13 empty] | Book 4: | [12 empty] | 2016-05-28 | Book 4: 362/PD/B-IDB/2016
MOM |  | 2016-03-16 | 183/BA.PP.IDB.DEDC/III/2016 | [26 empty] | 2016-03-22 | 196/BA.PP.IDB.DEDC/III/2016
|  | 2016-05-10 | 285/BA.PP.IDB.DEDC/V/2016 | [12 empty] | 20-21 Mei 016 | 327/BA.PP.IDB.DEDC/V/2016 | [12 empty] | 2016-05-28 | 363/BA.PP.IDB.DEDC/V/2016
Report | [57 empty] | Progress Report Jun, Jul, Agsts 2015 |  | Progress Report Jun, Jul, Agsts 2015 |  |  |  | Progress Report Jul, Agsts, Sep 2015
Payment | [57 empty] | 2015-09-28 | 016/WA/IDB/PL/IC/IX/2015 | 2015-09-28 | 020/WA/IDB/PL/IC/IX/2015 |  |  | 2015-10-02 | 024/WA/IDB/PL/IC/X/2015
|  |  | 1630212500 |  | 371650000 | [11 empty] | 1596980000 |  | 451785500 | [11 empty] | 2112288150 |  | 425500000 | [11 empty] | 874825000 |  | 212674500 | [11 empty] | 71250000 |  | 57000000 |  |  |  | 117160000
[59 empty] | 5221.69 |  | 4142.44 |  |  |  | 8514.53
Surat Perintah Pembukuan/Pengesahan (SP3) | [57 empty] | 2015-12-31 | 151403402001316 | 2015-12-31 | 151403402001317 |  |  | 2015-12-31 | 151403402001318
TERMIN 3 |  | Book 5-10: Final Report |  | 3: Bidding Evaluation Report of Contractors | [11 empty] | Book 5-10: Final Report |  | 3: Bidding Evaluation Report of Contractors | [11 empty] | Book 5-10: Final Report |  | 3: Bidding Evaluation Report of Contractors | [11 empty] | Book 5-10: Final Report |  | 3: Bidding Evaluation Report of Contractors | [11 empty] | Pembayaran Sep, Okt, Nov 2015 |  | Pembayaran Sep, Okt, Nov 2015 |  |  |  | Pembayaran Okt, Nov, Des 2015
Presentasi |  | 10-11 Mei 2016 | [13 empty] | 20-21 Mei 2016 | [13 empty] | 28-29 Mei 2016
|  | 8-9 Juni 2016 | [13 empty] | 2-4 & 8-11 Juni 2016 | [13 empty] | 7-10 & 30-4 Juni 2016
|  | 13-14 Juni 2015 | [13 empty] | 13-14 Juni 2015 | [13 empty] | 11-12 Juni 2016
Approval |  |  | Book 5: | [13 empty] | Book 5: | [13 empty] | Book 5:
|  |  | Book 6: | [13 empty] | Book 6: | [13 empty] | Book 6:
|  |  | Book 7: | [13 empty] | Book 7: | [13 empty] | Book 7:
|  |  | Book 8: | [13 empty] | Book 8: | [13 empty] | Book 8:
|  |  | Book 9: | [13 empty] | Book 9: | [13 empty] | Book 9:
|  |  | Book 10: | [13 empty] | Book 10: | [13 empty] | Book 10:
MOM |  | 2016-05-10 | 285/BA.PP.IDB.DEDC/V/2016
|  | 2016-06-14 | 407/BA.PP.IDB.DEDC/VI/2016
Report | [57 empty] | Progress Report Sep, Okt, Nov 2015 |  | Progress Report Sep, Okt, Nov 2015 |  |  |  | Progress Report Okt, Nov, Des 2015
NOL IDB/SFD
Payment | [57 empty] | 2015-12-01 | 028/WA/IDB/PL/IC/XII/2015 | 2015-12-01 | 032/WA/IDB/PL/IC/XII/2015 |  |  | 2016-02-25 | 011/WA/IDB/PL/IC/II/2016
|  |  | 1863100000 |  | 371650000 | [11 empty] | 1825120000 |  | 451785500 | [11 empty] | 2414043600 |  | 425500000 | [11 empty] | 999800000 |  | 212674500 | [11 empty] | 76104180 |  | 61570000 |  |  |  | 123383169
[59 empty] | 5526.81 |  | 4477.82
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 4 |  | Bank Guarantee, Approved 1st Certificate of Completion for Construction |  | 4: Physical Progress Report at 10% physical progress of building construction by Contractor | [11 empty] | Bank Guarantee, Approved 1st Certificate of Completion for Construction |  | 4: Physical Progress Report at 10% physical progress of building construction by Contractor | [11 empty] | Bank Guarantee, Approved 1st Certificate of Completion for Construction |  | 4: Physical Progress Report at 10% physical progress of building construction by Contractor | [11 empty] | Bank Guarantee, Approved 1st Certificate of Completion for Construction |  | 4: Physical Progress Report at 10% physical progress of building construction by Contractor | [11 empty] | Pembayaran Des 2015, Jan 2016, Feb 2016 |  | Pembayaran Des 2015, Jan 2016, Feb 2016 |  |  |  | Pembayaran Jan, Feb, Mar, Apr 2016
Presentasi
Approval
MOM
Report | [57 empty] | Progress Report Des 2015, Jan, Feb 2016 |  | Progress Report Des 2015, Jan, Feb 2016 |  |  |  | Progress Report Jan, Feb, Mar, Apr 2016
Bank Guarantee
First Certificate of Completion for Construction
Payment | [57 empty] | 2016-03-14 | 012/WA/IDB/PL/IC/III/2016 | 2016-03-14 | 013/WA/IDB/PL/IC/III/2016 |  |  | 2016-05-10 | 015/WA/IDB/PL/IC/V/2016
|  |  | 698662500 |  | 594640000 | [11 empty] | 684420000 |  | 722856800 | [11 empty] | 905266350 |  | 680800000 | [11 empty] | 374925000 |  | 340279200 | [11 empty] | 101178088 |  | 57000000 |  |  |  | 38000000
[59 empty] | 7610.24 |  | 4287.33
Surat Perintah Pembukuan/Pengesahan (SP3) | [63 empty] | 2016-09-14 | 161403402000627
TERMIN 5 |  |  |  | 5: Physical Progress Report at 20% physical progress of building construction by Contractor | [13 empty] | 5: Physical Progress Report at 20% physical progress of building construction by Contractor | [13 empty] | 5: Physical Progress Report at 20% physical progress of building construction by Contractor | [13 empty] | 5: Physical Progress Report at 20% physical progress of building construction by Contractor | [11 empty] | Pembayaran Mar, Apr, Mei 2016 |  | Pembayaran Mar, Apr, Mei 2016
Presentasi
Approval
MOM
Report | [57 empty] | Progress Report Mar, Apr, Mei 2016 |  | Progress Report Mar, Apr, Mei 2016
Payment | [57 empty] | 2016-06-03 | 018/WA/IDB/PL/IC/VI/2016 | 2016-06-03 | 017/WA/IDB/PL/IC/VI/2016
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200 | [11 empty] | 95675190 |  | 57000000
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 6 |  |  |  | 6: Physical Progress Report at 30% physical progress of building construction by Contractor | [13 empty] | 6: Physical Progress Report at 30% physical progress of building construction by Contractor | [13 empty] | 6: Physical Progress Report at 30% physical progress of building construction by Contractor | [13 empty] | 6: Physical Progress Report at 30% physical progress of building construction by Contractor
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 7 |  |  |  | 7: Physical Progress Report at 40% physical progress of building construction by Contractor | [13 empty] | 7: Physical Progress Report at 40% physical progress of building construction by Contractor | [13 empty] | 7: Physical Progress Report at 40% physical progress of building construction by Contractor | [13 empty] | 7: Physical Progress Report at 40% physical progress of building construction by Contractor
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 8 |  |  |  | 8: Physical Progress Report at 50% physical progress of building construction by Contractor | [13 empty] | 8: Physical Progress Report at 50% physical progress of building construction by Contractor | [13 empty] | 8: Physical Progress Report at 50% physical progress of building construction by Contractor | [13 empty] | 8: Physical Progress Report at 50% physical progress of building construction by Contractor
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 9 |  |  |  | 9: Physical Progress Report at 60% physical progress of building construction by Contractor | [13 empty] | 9: Physical Progress Report at 60% physical progress of building construction by Contractor | [13 empty] | 9: Physical Progress Report at 60% physical progress of building construction by Contractor | [13 empty] | 9: Physical Progress Report at 60% physical progress of building construction by Contractor
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 10 |  |  |  | 10: Physical Progress Report at 70% physical progress of building construction by Contractor | [13 empty] | 10: Physical Progress Report at 70% physical progress of building construction by Contractor | [13 empty] | 10: Physical Progress Report at 70% physical progress of building construction by Contractor | [13 empty] | 10: Physical Progress Report at 70% physical progress of building construction by Contractor
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 11 |  |  |  | 11: Physical Progress Report at 80% physical progress of building construction by Contractor | [13 empty] | 11: Physical Progress Report at 80% physical progress of building construction by Contractor | [13 empty] | 11: Physical Progress Report at 80% physical progress of building construction by Contractor | [13 empty] | 11: Physical Progress Report at 80% physical progress of building construction by Contractor
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 12 |  |  |  | 12: Physical Progress Report at 90% physical progress of building construction by Contractor | [13 empty] | 12: Physical Progress Report at 90% physical progress of building construction by Contractor | [13 empty] | 12: Physical Progress Report at 90% physical progress of building construction by Contractor | [13 empty] | 12: Physical Progress Report at 90% physical progress of building construction by Contractor
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 13 |  |  |  | 13: Physical Progress Report at 100% physical progress of building construction by Contractor ; Maintenance Manual, and Provisional Hand Over (PHO) Certificate | [13 empty] | 13: Physical Progress Report at 100% physical progress of building construction by Contractor ; Maintenance Manual, and Provisional Hand Over (PHO) Certificate | [13 empty] | 13: Physical Progress Report at 100% physical progress of building construction by Contractor ; Maintenance Manual, and Provisional Hand Over (PHO) Certificate | [13 empty] | 13: Physical Progress Report at 100% physical progress of building construction by Contractor ; Maintenance Manual, and Provisional Hand Over (PHO) Certificate
Presentasi
Approval
First Certificate of Completion for Construction
Payment
[5 empty] | 594640000 | [13 empty] | 722856800 | [13 empty] | 680800000 | [13 empty] | 340279200
Surat Perintah Pembukuan/Pengesahan (SP3)
TERMIN 14 |  |  |  | 14: Final Report and Certificate of Completion of the Supervision | [13 empty] | 14: Final Report and Certificate of Completion of the Supervision | [13 empty] | 14: Final Report and Certificate of Completion of the Supervision | [13 empty] | 14: Final Report and Certificate of Completion of the Supervision
Presentasi
Approval
Bank Guarantee |  |  |  |  | 371650000 | [13 empty] | 451785500 | [13 empty] | 425500000 | [13 empty] | 212674500
First Certificate of Completion for Construction
Payment
[5 empty] | 371650000 | [13 empty] | 451785500 | [13 empty] | 425500000 | [13 empty] | 212674500
Surat Perintah Pembukuan/Pengesahan (SP3)
|  |  | 4657750000 |  | 7433000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4562800000 |  | 9035710000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6035109000 |  | 8510000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2499500000 |  | 4253490000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 |  | 0 | [11 empty] | 0 |  | 0 | [11 empty] | 0 |  | 0 | [11 empty] | 0 |  | 0
[26 empty] | Procurement Committee: | [9 empty] | Procurement Committee:
[26 empty] | Chairman: M. Ilyas | [9 empty] | Chairman: Budi Hermono
[26 empty] | Member: Yasruddin | [9 empty] | Member: Mas Suryanto HS
[26 empty] | Member: Sarwadi | [9 empty] | Member: Agus Wiyono
[26 empty] | Member: Alfian Noor | [9 empty] | Member: Sanaji
[26 empty] | Member: Raisudin Azhari | [9 empty] | Member: Imaduddin
Member: M. Erwien Setiawan
Member: Lukman Ginanjar
Note on BY5: user: No covering letter
Note on BC22: user: Di Koran Tempo dan website Belmawa
Note on BE22: user: Di Koran Tempo dan website Belmawa
Note on BG22: user: di Koran Tempo
Note on BI22: user: Iklan di Koran Tempo
Note on BK22: user: Iklan di Koran Tempo
Note on BM22: user: Tanggal di iklan 29 Oktober 2014, tapi terbit di Konran Tempo tanggal 31 Oktober 2016
Note on BG29: user: MOM Submission EOI
Note on BI29: user: MOM Submission EOI
Note on BL29: user: Mom Submission EoI IC PS, FMS, dan ICTS
Note on BN29: user: MoM Opening EoI ICTS
Note on BX29: user: MoM Opening
Note on BG30: user: MOM Opening EOI
Note on BI30: user: MOM Opening EOI
Note on BL30: user: Mom Opening EoI IC PS, FMS, dan ICTS
Note on BN30: user: MoM Submission EoI ICTS
Note on M35: user: Gorontalo Post
Note on Q35: DS-IMHERE: dikirim ke IDB 19 Desember 2015
Note on AE35: DS-IMHERE: dikirim ke IDB 30 Desember 2014
Note on AS35: DS-IMHERE: dikirim ke SFD 19 Desember 2014
Note on AU35: user: Hardfile dikirim tanggal 8 September 2015
Note on BG35: user: tgl report-nya
Note on BI35: user: tgl report-nya
Note on BY35: user: revisi berdasarkan komentar IDB tanggl 18 Mei 2016
Note on J36: user: 1834.1 - 1834.31
Note on N36: user: 1834.1 - 1834.31
Note on E38: DS-IMHERE: diterima 8 April 2015 (Masih ada PT. Bina karya di dalam NOL)
Note on E48: DS-IMHERE: Mengirim revise RfP PMSC Paket 1
Note on E50: DS-IMHERE: Menigirim Revise ke dua RfP PMSC
Note on W57: user: http://lpse.untan.ac.id
Note on AO57: user: www.idb.uny.ac.id
Note on AU57: user: Revised document
Note on E58: DS-IMHERE: Penambahan 3 point pada RfP PMSC
Note on S58: DS-IMHERE: Penambahan 3 point pada RfP PMSC
Note on W58: 7 In 1: Pontianak Post
Note on AG58: DS-IMHERE: Penambahan 3 point pada RfP PMSC
Note on AO58: user: Tempo
Note on E59: DS-IMHERE: Mengirimkan kembali revise RfP PMSC dan komentar PMU
Note on S59: DS-IMHERE: Mengirimkan kembali revise RfP PMSC dan komentar PMU
Note on X59: user: 1834.1 - 1834.31
Note on AB59: user: 1834.1 - 1834.31
Note on AG59: DS-IMHERE: Mengirimkan kembali revise RfP PMSC dan komentar PMU
Note on AL59: user: 1834.1 - 1834.31
Note on AP59: user: 1834.1 - 1834.31
Note on D73: user: yang dapat NOL
Note on AE73: DS-IMHERE: dikirim ke IDB 29 April 2015
Note on C75: DS-IMHERE: Penambahan temlate summary
Note on C76: DS-IMHERE: Resend TER ke ibu Enggar dengan mengevaluasi region
Note on E80: idb7in1: CD yang berisi dokumen lengkap dikirim ke CGO tgl 7 Oktober 2015
Note on I81: user: Tanggal 10 Mei 2016 mengirim Report PQD 6 Universitas melalui FD
Note on J81: user: tanggal surat: 3 Mei 2016
Note on M81: user: Tanggal 10 Mei 2016 mengirim Report PQD 6 Universitas melalui FD
Note on N81: user: tanggal surat: 3 Mei 2016
Note on W81: user: Tanggal 10 Mei 2016 mengirim Report PQD 6 Universitas melalui FD
Note on X81: user: tanggal surat: 3 Mei 2016
Note on AA81: user: Tanggal 10 Mei 2016 mengirim Report PQD 6 Universitas melalui FD
Note on AB81: user: tanggal surat: 3 Mei 2016
Note on AK81: user: Tanggal 10 Mei 2016 mengirim Report PQD 6 Universitas melalui FD
Note on AL81: user: tanggal surat: 3 Mei 2016
Note on AO81: user: Tanggal 10 Mei 2016 mengirim Report PQD 6 Universitas melalui FD
Note on AP81: user: tanggal surat: 3 Mei 2016
Note on AT92: user: Extended approval TER & PT. Bina Karya
Note on F96: user: 060.1 - 060.4
Note on I96: user: Soft file Bid Doc, RKS, BoQ dan Gambar dikirim tanggal 30 Agustus 2016
Note on M96: user: Soft file Bid Doc, RKS, BoQ dan Gambar dikirim tanggal 30 Agustus 2016
Note on T96: user: 064.1 - 064.3
Note on W96: user: Soft file Bid Doc, RKS, BoQ dan Gambar dikirim tanggal 30 Agustus 2016
Note on AA96: user: Soft file Bid Doc, RKS, BoQ dan Gambar dikirim tanggal 30 Agustus 2016
Note on AH96: user: 067.1 - 067.4
Note on AK96: user: Soft file Bid Doc, RKS, BoQ dan Gambar dikirim tanggal 30 Agustus 2016
Note on AO96: user: Soft file Bid Doc, RKS, BoQ dan Gambar dikirim tanggal 30 Agustus 2016
Note on AV96: user: 035.1 - 035.5
Note on AY96: user: Hardfile dikirim ke SFD tanggal 13 Oktober 2016
Note on C100: idb7in1: Hardfile report dikirm tanggal 7 Oktober ke CGO setelah mendapat NOL
Note on AS100: user: Hardfile dikirim 20 Agustus 2015
Note on AU100: user: softcopy dan hardcopy dikirim tgl 27 januari 2016
Note on BJ110: user: Persiapan kontrak dan detail rencana kerja yang akan dilaksanakan
Note on C115: idb7in1: CD report dikirim ke CGO tanggal 8 Nov 15
Note on Q115: idb7in1: CD report dikirim ke CGO tanggal 8 Nov 15
Note on AE115: idb7in1: CD report dikirim ke CGO tanggal 8 Nov 15
Note on AV115: user: semula dikirim tanggal 26 Mei 2016 no. 355/B/SFD/PMU-7in1/2016, namun karena ada kesalahan penulisan nilai kontrak di covering letter maka dikirim kembali (revisi CL) tanggal 13 Juli 2016
Note on AS122: user: hardfile dikirim 15 januari 2016
Note on BM139: user: 2015: 9 bulan 2016: 3 bulan 2017: 3 bulan
Note on D141: user: IDB 4.657.750.000 PPN 465.775.000 total 5.123.525.000
Note on F141: user: IDB 7.433.000.000 PPN 743.300.000 total 8.176.300.000
Note on R141: user: IDB 4.562.800.000 PPN 452.800.000 total 5.019.080.000
Note on T141: user: IDB 9.035.710.000 PPN 903.571.000 total 9.939.281.000
Note on AF141: user: IDB 6.035.109.000 PPN 603.510.900 total 6.638.619.900
Note on AH141: user: IDB 8.510.000.000 PPN 851.000.000 total 9.361.000.000
Note on AT141: user: SFD 2.499.500.000 PPN 249.950.000 total 2.749.450.000
Note on AV141: user: SFD 4.253.490.000 PPN 425.349.000 total 4.678.839.000
Note on B146: user: tanggal diterimanya report
Note on BH149: user: sesuai NOD
Note on BJ149: user: sesuai NOD
Note on BN149: user: sesuai NOD
Note on C152: user: Book 2
Note on Q152: user: Book 2
Note on AE152: user: Book 2
Note on C153: user: book 3-10
Note on Q153: user: Book 3-10
Note on AE153: user: Book 3-10
Note on D157: user: Berita Acara Pembahasan Second Preliminary Report DEDC P1
Note on R157: user: Berita Acara Pembahasan Second Preliminary DEDC P2
Note on AF157: user: Berita Acara Pembahasan Second Preliminary Report DEDC P3
Note on D158: user: Berita Acara Kemajuan Book 3-10 DEDC P1
Note on R158: user: Berita Acara Pembahasan Kemajuan Book 3-10 DEDC P2
Note on AF158: user: Berita Acara Pembahasan Kemajuan Book 3-10 DEDC P3
Note on BH163: user: sesuai NOD
Note on BJ163: user: sesuai NOD
Note on BN163: user: sesuai NOD
Note on C166: user: book 3-10
Note on Q166: user: Book 3-10
Note on AE166: user: book 3-10
Note on C167: user: Presentasi Book 5-10 di PIU
Note on Q167: user: 2-4 Juni: Presentasi Book 5-10 di PIU Untan 8-11 Juni: Presentasi Book 5-10 di PIU Unlam
Note on AE167: user: 7-10 Juni: Presentasi Book 5-10 di PIU Unesa 30 Mei-4 Juni: Presentasi Book 5-10 di PIU UNY
Note on C168: user: Presentasi Book 5-10 di PMU
Note on Q168: user: Presentasi Book 5-10 di PMU
Note on AE168: user: Presentasi Book 5-10 di PMU
Note on D175: user: Berita Acara Kemajuan Book 3-10 DEDC P1
Note on D176: user: Berita Acara Pembahasan dan Evaluasi Revisi Book 5-10 DEDC Paket 1
Note on BH182: user: sesuai NOD
Note on BJ182: user: sesuai NOD
Note on BH193: user: sesuai NOD
Note on BJ193: user: sesuai NOD
Note on F262: user: akan dikembalikan setelah PMSC menyerahkan Sertifikat Penyelesaian pengawasan masa pemeliharaan
Note on T262: user: akan dikembalikan setelah PMSC menyerahkan Sertifikat Penyelesaian pengawasan masa pemeliharaan
Note on AH262: user: akan dikembalikan setelah PMSC menyerahkan Sertifikat Penyelesaian pengawasan masa pemeliharaan
Note on AV262: user: akan dikembalikan setelah PMSC menyerahkan Sertifikat Penyelesaian pengawasan masa pemeliharaan

## NO KONTRAK
PENOMORAN KONTRAK PENGADAAN |  |  |  | PENOMORAN ADDENDUM KONTRAK PENGADAAN
No Kontrak |  | Tanggal Kontrak | Nama Kontrak | No Kontrak |  | Tanggal Kontrak | Nama Kontrak
001 | /IC/IDB/K/II/2015 | 2015-02-26 | PMU Experts - Financial Management Specialist | 001 | /IC/IDB/AD/V/2015 | 2015-05-29 | PMU Experts - Financial Management Specialist
002 | /IC/IDB/K/II/2015 | 2015-02-27 | PMU Experts - Procurement Specialist | 001 | /IC/IDB/AD/V/2015 | 2015-05-29 | PMU Experts - Procurement Specialist
003 | /IC/IDB/K/III/2015 | 2015-03-25 | PMU Experts - Information and Communication Technology Specialist | 001 | /IC/IDB/AD/V/2015 | 2015-05-29 | PMU Experts - Information and Communication Technology Specialist
004 | /DEDC/IDB/K/XII/2015 | 2015-12-16 | DEDC Package 1
005 | /DEDC/IDB/K/XII/2015 | 2015-12-16 | DEDC Package 2
006 | /DEDC/IDB/K/XII/2015 | 2015-12-16 | DEDC Package 3
007 | /DEDC.SFD/K/I/2016 | 25 Januari 2016 | DEDC Package 4
007 | /B/7IN1/K/XII/2015 | 2015-12-31 | Sewa - Menyewa Ruangan Kantor
008 | /PMSC/IDB/K/V/2016 | 2016-05-30 | PMSC Package 1
009 | /PMSC/IDB/K/V/2016 | 2016-05-30 | PMSC Package 2
010 | /PMSC/IDB/K/V/2016 | 2016-05-30 | PMSC Package 3
011 | /PMSC/SFD/K/VII/2016 | 21 Juli 2016 | PMSC Package 4
012 | /IC/IDB/K/X/2016 | 2016-11-01 | PMU Experts - Civil Engineering Specialist

## Data Kontrak
DATA KONTRAK PROYEK 7 IN 1
No. | Paket | PMU / PIU | Konsultan Pemenang | Penandatangan Kontrak | Kontrak |  | PIC
[5 empty] | Mulai | Akhir
1 | DEDC Paket 1 | Unsrat - UNG | PT. Patroon Arsindo | Firmansyah (Direktur Utama) | 2015-12-16 | 2016-06-16 | Prayitno (staf) | 0813 1711 8040
2 | DEDC Paket 2 | Untan - Unlam | JV: PT. Artefak Arkindo - PT. Disiplan | Bambang Suprihadi (Direktur PT. Artefak Arkindo) | 2015-12-16 | 2016-06-16 | Bambang S (Direktur / Co Team Leader) | 0816 1940 252
[7 empty] | Bu Nana (staf) | 0812 8077 6852
3 | DEDC Paket 3 | Unesa - UNY | JV: PT. Widha - PT. Pola Data Consultant | Mohamad Budiono (Direktur PT. Widha) | 2015-12-16 | 2016-06-16 | Ronny ABW (Team Leader) | 0813 9059 4949
[7 empty] | Irma Hidayati (staf admin) | 0815 6534 760
[7 empty] | Revianto Budi (Co Team Leader) | 0812 2959 441
[7 empty] | Astri (staf Pola Data Consultant) | 0813 1514 3444
4 | DEDC Paket 4 | Unsyiah | PT. Supernova Jaya Mandiri | Hendra Saputra (Direktur Utama) | 2016-01-25 | 2016-07-25 | Zainal | 0852 6229 8273
[7 empty] | Bu Nana (Keuangan) | 0812 6980 8041
5 | PMSC Paket 1 | Unsrat - UNG | PT. Griksa Cipta | Aswin Griksa | 30 Mei 2016 |  | Aswin Griksa (Direktur Utama) | 0811 946 973
[7 empty] | Bachtiar Wairooy (Team Leader) | 0812 8124 291 / 0818 0800 9545
[7 empty] | Dian (Manajer) | 0812 1061 843
[7 empty] | Kris Tjandra (Staf) | 0812 7724 6299
6 | PMSC Paket 2 | Untan - Unlam | PT. Deta Decon | Chairul Basri Nasution | 30 Mei 2016 |  | Mardiana Daoed (Direktur) | 0811 875 912
[7 empty] | Wuryan Irianto (Team Leader) | 0812 9390 675
[7 empty] | Wahyu Raharjo (Co Team Leader) | 0812 6884 7016
[7 empty] | Novvy Riza Pahlevy (staf) | 0815 166 8379
7 | PMSC Paket 3 | Unesa - UNY | JV: PT. Cakra Manggilingan Jaya - PT. Adhicipta Engineering Consultant | Priyono | 30 Mei 2016 |  | Agung Pius (Direktur) | 0813 1041 8634
[7 empty] | Budhi Prayogo (Team Leader) | 0822 8374 6703
8 | PMSC Paket 4 | Unsyiah | PT. Kogas Driyap Konsultan |  |  |  | Dudu Abdullah (Manajer) | 0811 1188 547
9 | PMU Experts: Financial Management Specialist | PMU | Wadiyo | Wadiyo | 2015-03-02 | 2017-12-31 | Wadiyo | 0856 9522 6176
10 | PMU Experts: Procurement Specialist | PMU | Sutarno | Sutarno | 2015-03-02 | 2016-12-31 | Sutarno | 0858 8366 8716
11 | PMU Experts: Information and Communication Technology Specialist | PMU | Avinanta Tarigan | Avinanta Tarigan | 2015-04-01 | 2017-12-31 | Avinanta Tarigan | 0817 6771 768
[7 empty] | Nur Aizat (Asisten) | 0812 1687 8825
[7 empty] | Ghaffar (Asisten) | 0853 5821 0035
12 | PMU Experts: Civil Engineering Specialist | PMU

## Data Report
OUTPUT |  | DEDC PAKET 1 |  |  | DEDC PAKET 2 |  |  | DEDC PAKET 3 |  |  | DEDC PAKET 4
|  | JUMLAH (bdskn kontrak) | APPROVAL | KETERANGAN | JUMLAH (bdskn kontrak) | APPROVAL | KETERANGAN | JUMLAH (bdskn kontrak) | APPROVAL | KETERANGAN | JUMLAH (bdskn kontrak) | APPROVAL | KETERANGAN
Book 1 | First Preliminary Report | 5 eksemplar | v | Presentasi di PMU: 20-21 Januari 2016 Disetujui PMU & PIU: 29 Januari 2016 Diserahkan ke PMU: 9 Februari 2016 | 10 eksemplar | v | Presentasi di PMU: 19-20 Februari 2016 Disetujui PMU & PIU: 18 Maret 2016 Diserahkan ke PMU: 26 April 2016 | 8 eksemplar | v | Presentasi di PMU: 12-13 Januari 2016 Disetujui PMU & PIU: 19 Januari 2016 Diserahkan ke PMU: 20 Januari 2016 | 5 eksemplar | v | Sudah mengumpulkan Book 1 tanggal 18 Mei 2016, namun masih menunggu versi bahasa Indonesia
Book 2 | Second Preliminary Report | 5 eksemplar |  | Sudah dipaparkan tanggal 16-17 Maret 2016 dan sedang proses revisi. | 10 eksemplar |  | Sudah dipaparkan tanggal 18-19 Maret 2016 dan sedang proses revisi. | 8 eksemplar | v | Sudah dipaparkan tanggal 20-21 Maret 2016 dan sedang proses revisi. Disetujui PMU & PIU: 28 Mei 2016 | 5 eksemplar |  | Sudah dipaparkan tanggal 18-19 Mei 2016 dan sedang proses revisi. Sesuai berita acara tanggal 18 Mei 2016 akan diserahkan tanggal 25 Mei 2016 ke PIU untuk di-review
Book 3 | First Progress Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 10-11 Mei 2016 akan diserahkan tanggal 13 Mei 2016 ke PIU untuk di-review | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar | v | Sudah dipaparkan tanggal 28-29 Mei 2016. Disetujui PMU & PIU: 28 Mei 2016 | 5 eksemplar |  | Sudah dipaparkan tanggal 18-19 Mei 2016 dan sedang proses revisi. Sesuai berita acara tanggal 18 Mei 2016 akan diserahkan tanggal 25 Mei 2016 ke PIU untuk di-review
Book 4 | Second Progress Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 10-11 Mei 2016 akan diserahkan tanggal 13 Mei 2016 ke PIU untuk di-review | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar | v | Sudah dipaparkan tanggal 28-29 Mei 2016. Disetujui PMU & PIU: 28 Mei 2016 | 5 eksemplar |  | Sudah dipaparkan tanggal 18-19 Mei 2016 dan sedang proses revisi. Sesuai berita acara tanggal 18 Mei 2016 akan diserahkan tanggal 25 Mei 2016 ke PIU untuk di-review
Book 5 | Final Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 10-11 Mei 2016 akan diserahkan tanggal 5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 7-10 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar |  | Sudah dipaparkan tanggal 28-29 Mei 2016. Sesuai berita acara tanggal 28-29 Mei 2016 akan diserahkan tanggal 6 Juni 2016 ke PIU UNY untuk di-review. Akan dipresentasikan di PIU UNY tanggal 30 Mei - 3 Juni 2016 dan di PMU tanggal 11-12 Juni 2016. | 10 eksemplar
Book 6 | Final Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 10-11 Mei 2016 akan diserahkan tanggal 23 Mei 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 7-10 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar |  | Sudah dipaparkan tanggal 28-29 Mei 2016. Sesuai berita acara tanggal 28-29 Mei 2016 akan diserahkan tanggal 6 Juni 2016 ke PIU UNY untuk di-review. Akan dipresentasikan di PIU UNY tanggal 30 Mei - 3 Juni 2016 dan di PMU tanggal 11-12 Juni 2016. | 10 eksemplar
Book 7 | Final Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 10-11 Mei 2016 akan diserahkan tanggal 6 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 7-10 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar |  | Sudah dipaparkan tanggal 28-29 Mei 2016. Sesuai berita acara tanggal 28-29 Mei 2016 akan diserahkan tanggal 6 Juni 2016 ke PIU UNY untuk di-review. Akan dipresentasikan di PIU UNY tanggal 30 Mei - 3 Juni 2016 dan di PMU tanggal 11-12 Juni 2016. | 10 eksemplar
Book 8 | Final Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 10-11 Mei 2016 akan diserahkan tanggal 30 Mei 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 7-10 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar |  | Sudah dipaparkan tanggal 28-29 Mei 2016. Sesuai berita acara tanggal 28-29 Mei 2016 akan diserahkan tanggal 6 Juni 2016 ke PIU UNY untuk di-review. Akan dipresentasikan di PIU UNY tanggal 30 Mei - 3 Juni 2016 dan di PMU tanggal 11-12 Juni 2016. | 10 eksemplar
Book 9 | Final Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 6 Juni 2016 akan diserahkan tanggal 30 Mei 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 7-10 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar |  | Sudah dipaparkan tanggal 28-29 Mei 2016. Sesuai berita acara tanggal 28-29 Mei 2016 akan diserahkan tanggal 6 Juni 2016 ke PIU UNY untuk di-review. Akan dipresentasikan di PIU UNY tanggal 30 Mei - 3 Juni 2016 dan di PMU tanggal 11-12 Juni 2016. | 10 eksemplar
Book 10 | Final Report | 5 eksemplar |  | Sudah dipaparkan tanggal 10-11 Mei 2016. Sesuai berita acara tanggal 6 Juni 2016 akan diserahkan tanggal 30 Mei 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 7-10 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 10 eksemplar |  | Sudah dipaparkan tanggal 20-21 Mei 2016. Sesuai berita acara tanggal 20-21 Mei 2016 akan diserahkan tanggal 3-5 Juni 2016 ke PIU untuk di-review. Akan dipresentasikan di PIU tanggal 8-11 Juni 2016 dan di PMU tanggal 13-14 Juni 2016. | 8 eksemplar |  | Sudah dipaparkan tanggal 28-29 Mei 2016. Sesuai berita acara tanggal 28-29 Mei 2016 akan diserahkan tanggal 6 Juni 2016 ke PIU UNY untuk di-review. Akan dipresentasikan di PIU UNY tanggal 30 Mei - 3 Juni 2016 dan di PMU tanggal 11-12 Juni 2016. | 10 eksemplar
| Maket | 2 unit | [5 empty] | Unesa: 2 unit UNY: 14 paket |  |  | 1 unit
| 3D Animation / Visual Animation | 8 menit |  |  | 30 menit | [5 empty] | min 10 menit

## PerpanjangPenawaranDEDC
DEDC - TECHNICAL PROPOSAL
Paket | No. | Perusahaan | Surat Penawaran |  |  | Surat Perpanjangan I |  |  | Surat Perpanjangan II |  |  | Surat Perpanjangan III
|  |  | Tgl Surat dr PMU | Tgl Surat Prshn | Srt Prshn s/d Tgl | Tgl Surat dr PMU | Tgl Surat Prshn | Srt Prshn s/d Tgl | Tgl Surat dr PMU | Tgl Surat Prshn | Srt Prshn s/d Tgl | Tgl Surat dr PMU | Tgl Surat Prshn | Srt Prshn s/d Tgl
1 | 1 | PT. Artefak Arkindo - PT. Disiplan Consult (JV) |  | 2015-02-16 | 2015-05-17 | 2015-05-15 |  |  | 2015-08-14 |  | 2015-10-17
| 2 | PT. Bina Karya
| 3 | PT. Gitarencana Multiplan |  | 2015-02-16 | 2015-05-17 | 2015-05-15 | 2015-02-16 | 2015-07-17 | 2015-08-14 |  | 2015-10-17
| 4 | PT. Patroon Arsindo |  | 2015-02-16 | 2015-05-17 | 2015-05-15 | 2015-02-16 | 2015-07-17 | 2015-08-14 |  | 2015-10-17 | 2015-10-10 | 2015-10-12 | 2016-01-17
| 5 | PT. Virama Karya |  | 2015-02-16 | 2015-05-17 | 2015-05-15 | 2015-05-28 | 2015-07-17
| 6 | PT. Yaika Gema Utama - PT. Arkonin Engineering Manggala Pratama (JO) |  | 2015-02-16 | 2015-05-17 | 2015-05-15 |  |  | 2015-08-14 |  | 2015-10-17
| 7 | PT. Yodya Karya |  | 2015-02-13 | 2015-05-17 | 2015-05-15 | 2015-06-09 | 2015-07-17 | 2015-08-14 |  | 2015-10-17
2 | 1 | PT. Artefak Arkindo - PT. Disiplan (JV) |  | 2015-03-30 | 2015-06-28 | 2015-06-25 | 2015-06-30 | 2015-09-26 | 2015-09-21 | 2015-09-28 | 2015-12-26
| 2 | PT. Bina Karya (Persero) - PT. Gitarencana Multiplan (JO)
| 3 | PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) |  | 2015-03-30 | 2015-06-28 | 2015-06-25 | 2015-03-30 | 2015-09-26 | 2015-09-21
| 4 | PT. Patroon Arsindo - PT. Griksa Cipta (JO) |  | 2015-03-30 | 2015-06-28 | 2015-06-25 | 2015-06-25 | 2015-09-26
| 5 | PT. Virama Karya |  | 2015-03-30 | 2015-06-28 | 2015-06-25
| 6 | PT. Yodya Karya (Wilayah III Jakarta) |  | 2015-03-30 | 2015-06-28 | 2015-06-25 | 2015-06-29 | 2015-09-26
3 | 1 | PT. Bina Karya (Persero)
| 2 | PT. Deta Decon |  | 2015-03-09 | 2015-06-10 | 2015-06-08 | 2015-06-22 | 2015-09-10 | 2015-09-08 | 2015-09-09 | 2015-12-10
| 3 | PT. Gitarencana Multiplan |  | 2015-03-09 | 2015-06-10 | 2015-06-08 | 2015-06-22 | 2015-09-10
| 4 | PT. Griksa Cipta - PT. Arkonin Engineering Manggala Pratama (JO) |  | 2015-03-09 | 2015-06-10 | 2015-06-08 | 2015-06-17 | 2015-09-10 | 2015-09-08 | 2015-09-17 | 2015-12-10
| 5 | PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  | 2015-03-09 | 2015-06-10 | 2015-06-08
| 6 | PT. Widha - PT. Pola Data Konsultan (JO) |  | 2015-03-09 | 2015-06-10 | 2015-06-08 | 2015-06-18 | 2015-09-10 | 2015-09-08 | 2015-09-10 | 2015-12-10 | 2015-12-01 | 2015-12-07 | 2016-03-11
| 7 | PT. Yodya Karya |  | 2015-03-09 | 2015-06-10 | 2015-06-08 | 2015-06-17 | 2015-09-10
4 | 1 | PT. Bina Karya - PT. Garis Rancang Bangun (JO) |  | 2015-03-23 | 2015-06-24 | 2015-06-18 | 2015-06-29 | 2015-09-19 | 2015-09-15 |  | 2015-12-19
| 2 | PT. Gitarencana Multiplan |  | 2015-03-23 | 2015-06-24 | 2015-06-18 | 2015-06-29 |  | 2015-09-15 | 2015-09-17 | 2015-12-19
| 3 | PT. Perentjana Djaja |  | 2015-03-23 | 2015-06-24 | 2015-06-18 |  |  | 2015-09-15 |  | 2015-12-19
| 4 | PT. Supernova Jaya Mandiri |  | 2015-03-23 | 2015-06-24 | 2015-06-18 | 2015-03-20 | 2015-09-19 | 2015-09-15 | 2015-03-20 | 2015-12-19 | 2015-12-17

## PerpanjangPenawaranPMSC
PMSC - TECHNICAL PROPOSAL
Paket | No. | Perusahaan | Surat Penawaran |  |  | Surat Perpanjangan I |  |  | Surat Perpanjangan II
|  |  | Tgl Surat dr PMU | Tgl Surat Prshn | Srt Prshn s/d Tgl | Tgl Surat dr PMU | Tgl Surat Prshn | Srt Prshn s/d Tgl | Tgl Surat dr PMU | Tgl Surat Prshn | Srt Prshn s/d Tgl
1 | 1 | PT. Artefak Arkindo - PT. Garis Rancang Bangun (JV) |  | 2015-07-23 | 2015-10-20 | 2015-10-15 | 2015-10-20 | 2016-01-22 | 2016-01-19 | 2016-01-22 | 2016-04-21
| 2 | PT. Duta Hari Murthi Konsultan - PT. Cakrabuana Consultants (JV) |  | 2015-07-23 | 2015-10-20 | 2015-10-15 | 2015-10-16 | 2016-01-22 | 2016-01-19 | 2016-01-20 | 2016-04-21
| 3 | PT. Griksa Cipta |  | 2015-07-23 | 2015-10-20 | 2015-10-15 | 2015-01-04 | 2016-01-22 | 2016-01-19 | 2016-01-20 | 2016-04-21
| 4 | PT. Kogas Driyap Konsultan |  | 2015-07-22 | 2015-10-20 | 2015-10-15 | 2015-12-29 | 2016-01-22 | 2016-01-19 | 2016-01-20 | 2016-04-21
2 | 1 | PT. Artefak Arkindo |  | 2015-06-22 | 2015-09-20 | 2015-09-13 | 2015-09-20 | 2015-12-21 | 2015-12-15 | 2015-12-21 | 2016-03-20
| 2 | PT. Deta Decon |  | 2015-06-22 | 2015-09-20 | 2015-09-13 | 2016-09-17 | 2015-12-21 | 2015-12-15 | 2015-12-16 | 2015-03-23
| 3 | PT. Duta Hari Murthi Konsultan - PT. Arkonin EMP (JO) |  | 2015-06-22 | 2015-09-20 | 2015-09-13 | 2015-09-14 | 2015-12-21 | 2015-12-15 | 2015-12-16 | 2016-03-20
3 | 1 | PT. Cakra Manggilingan Jaya - PT. Adhicipta Engineering Consultant (JV) |  | 2015-06-26 | 2015-09-24 | 2015-09-16 | 2015-09-21 | 2015-12-24 | 2015-12-16 | 2015-12-24 | 2016-03-23
| 2 | PT. Sangkuriang |  | 2015-06-25 | 2015-09-24 | 2015-09-16 | 2015-09-21 | 2015-12-24 | 2015-12-16 | 2015-12-21 | 2015-03-23
| 3 | PT. Virama Karya |  | 2015-06-26 | 2015-09-24 | 2015-09-16 | 2015-09-20 | 2015-12-24 | 2015-12-16 | 2015-12-20 | 2016-03-23
| 4 | PT. Yodya Karya - PT. Gitarencana Multiplan (JV) |  | 2015-06-26 | 2015-09-24 | 2015-09-16 | 2015-09-21 | 2015-12-24 | 2015-12-16 | 2015-12-17 | 2016-03-23
4 | 1 | Al-Rajhi Engineering |  |  |  | 2016-01-05 | 2016-01-30 | 2016-04-24
| 2 | Alteraz Design JO Kiklop Design Eng |  |  |  | 2016-01-05 | 2016-01-28 | 2016-04-24
| 3 | PT. Deta Decon |  |  |  | 2016-01-05 | 2016-01-07 | 2016-04-24
| 4 | PT. Kogas Driyap Konsultan |  |  |  | 2016-01-05 | 2016-01-12 | 2016-04-24
| 5 | PT. Maxitech Utama Indonesia |  |  |  | 2016-01-05

## KATALOG
KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN |  |  |  |  | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 1 | [5 empty] | DEDC PAKET 2 | [5 empty] | PMSC PAKET 1 |  |  |  |  | PMSC PAKET 2
DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS
Short-Listing Original | 1. PT. Patroon Arsindo |  |  |  |  | Short-Listing Original | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku |  |  |  | Technical Proposal | 1. PT. Kogas Driyap Konsultan |  | 1 ori + 3 copy | Kontainer 15 | Technical Proposal | 1. PT. Artefak Arkindo |  | 3 copy | Kontainer 18
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | [5 empty] | 2. PT. Yodya Karya (Wilayah III Jakarta) | [5 empty] | 2. PT. Griksa Cipta |  | 3 copy |  |  | PT. Artefak Arkindo |  | 1 ori | Kontainer 19
| 3. PT. Yodya Karya | [5 empty] | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) | [5 empty] | 3. JV: PT. Artefak Arkindo - PT. Garis Rancang Bangun |  | 1 ori + 3 copy | Kontainer 16 |  | 2. PT. Deta Decon | 2 buku | 3 copy
| 4. PT. Darena Prakarsa Utama | [5 empty] | 4. PT. Virama Karya (Persero) | [5 empty] | 4. JV: PT. Duta Hari Murthi Konsultan - PT. Cakrabuana Consultants |  | 1 ori + 3 copy |  |  | 3. PT. Duta Hari Murthi Konsultan - PT. Arkonin EMP (JO) |  | 1 ori + 3 copy
| 5. PT. Gitarencana Multiplan | [5 empty] | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 6. PT. Pandu Persada |  |  |  |  | Short-Listing Copy | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku |  | Kardus 7
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | [5 empty] | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 8. PT. Virama Karya (Pesero) | [5 empty] | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
Short-Listing Copy | 1. PT. Patroon Arsindo |  |  | Kardus 10 |  |  | 4. PT. Virama Karya (Persero)
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku |  |  |  |  | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 3. PT. Yodya Karya | [5 empty] | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku |  | Kardus 8
| 4. PT. Darena Prakarsa Utama | [5 empty] | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 5. PT. Gitarencana Multiplan | [5 empty] | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
| 6. PT. Pandu Persada | [5 empty] | 4. PT. Virama Karya (Persero)
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku |  |  |  |  | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 8. PT. Virama Karya (Pesero) | [5 empty] | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku |  | Kardus 9
| 1. PT. Patroon Arsindo |  |  | Kardus 11 |  |  | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku |  |  |  |  | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
| 3. PT. Yodya Karya | [5 empty] | 4. PT. Virama Karya (Persero)
| 4. PT. Darena Prakarsa Utama | [5 empty] | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 5. PT. Gitarencana Multiplan |  |  |  |  | Technical Proposal | 1. PT. Artefak - PT. Disiplan (JO) |  | 3 copy | Kontainer 5
| 6. PT. Pandu Persada | [5 empty] | 2. PT. Virama Karya (Persero) |  | 1 ori + 3 copy
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku |  |  | Yaika kurang buku 2 & 3 |  | 3. PT.Patroon Arsindo - PT. Griksa Cipta (JO) |  | 1 ori + 3 copy
| 8. PT. Virama Karya (Pesero) | [5 empty] | 4. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) |  | 1 ori + 2 copy | Kontainer 6
| 1. PT. Patroon Arsindo |  |  | Kardus 12 |  |  | 5. PT. Yodya Karya (Wilayah III Jakarta) |  | 1 ori + 3 copy
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku |  |  |  |  | PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) |  | 1 copy | Kontainer 7
| 3. PT. Yodya Karya | [5 empty] | PT. Patroon Arsindo - PT. Griksa Cipta (JO) |  | 1 ori + 1 copy
4. PT. Darena Prakarsa Utama
5. PT. Gitarencana Multiplan
6. PT. Pandu Persada
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku | [8 empty] | Yodya kurang 1
8. PT. Virama Karya (Pesero)
Technical Proposal | 1. Yodya Karya | 2 buku | 1 ori + 3 copy | Kontainer 1
| 2. Virama Karya |  | 1 ori + 3 copy
| 3. Yaika Gama Utama - PT. Arkonin Engineering Manggala Pratama (JO) | 2 buku | 1 ori + 3 copy | Kontainer 2
| 4. Gitarencana Multiplan |  | 1 ori + 3 copy | Kontainer 3
| 5. Patroon Arsindo |  | 3 copy
| 6. Artefak Arkindo - PT. Disiplan (JO) | 2 buku | 1 ori + 3 copy | Kontainer 4
KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN |  |  |  |  | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 3 | [5 empty] | DEDC PAKET 4 | [5 empty] | PMSC PAKET 3 |  |  |  |  | PMSC PAKET 4
DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS
Short-Listing Original | 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku |  |  |  | Short-Listing Original | 1. PT. Kogas Driyap Konsultan |  |  |  |  | Technical Proposal | 1. JV: PT. Cakra Manggilingan Jaya - PT. Adhicipta Engineering Consultant |  | 1 ori + 3 copy | Kontainer 16 | Technical Proposal | 1. Al-Rajhi for Engineering Consultation |  | 1 ori + 4 copy | Kontainer 20
| 2. PT. Gitarencana Multiplan | [5 empty] | 2. PT. Perentjana Djaja | [5 empty] | 2. JV: PT. Yodya Karya - PT. Gitarencana Multiplan |  | 1 ori + 3 copy | Kontainer 17 |  | 2. Alteraz Design |  | 1 ori + 4 copy
| 3. PT. Deta Decon | [5 empty] | 3. PT. Gitarencana Multiplan | [5 empty] | 3. PT. Sangkuriang |  | 1 ori + 3 copy |  |  | 3. PT. Deta Decon |  | 1 ori + 3 copy
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) | [5 empty] | 4. PT. Yodya Karya (Wilayah III Jakarta) | [5 empty] | 4. PT. Virama Karya | 2 buku | 1 ori + 3 copy | Kontainer 18 |  | 4. PT. Kogas Driyap Konsultan |  | 3 copy
| 5. PT. Arkitek Tema Empat | [5 empty] | 5. PT. Supernova Jaya Mandiri | [10 empty] | 5. PT. Maxitech Utama Indonesia |  | 1 ori + 3 copy
| 6. PT. Griksa Cipta - PT. Arkonin (JO) | [5 empty] | 6. PT. Arkitek Team Empat
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  |  | Short-Listing Original | 1. PT. Kogas Driyap Konsultan |  |  | Kardus 4
Short-Listing Copy | 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku |  | Kardus 1 |  |  | 2. PT. Perentjana Djaja
| 2. PT. Gitarencana Multiplan | [5 empty] | 3. PT. Gitarencana Multiplan
| 3. PT. Deta Decon | [5 empty] | 4. PT. Yodya Karya (Wilayah III Jakarta)
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) | [5 empty] | 5. PT. Supernova Jaya Mandiri
| 5. PT. Arkitek Tema Empat | [5 empty] | 6. PT. Arkitek Team Empat
| 6. PT. Griksa Cipta - PT. Arkonin (JO) | [5 empty] | 1. PT. Kogas Driyap Konsultan |  |  | Kardus 5
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  |  |  | 2. PT. Perentjana Djaja
| 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku |  | Kardus 2 |  |  | 3. PT. Gitarencana Multiplan
| 2. PT. Gitarencana Multiplan | [5 empty] | 4. PT. Yodya Karya (Wilayah III Jakarta)
| 3. PT. Deta Decon | [5 empty] | 5. PT. Supernova Jaya Mandiri
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) | [5 empty] | 6. PT. Arkitek Team Empat
| 5. PT. Arkitek Tema Empat | [5 empty] | 1. PT. Kogas Driyap Konsultan |  |  | Kardus 6
| 6. PT. Griksa Cipta - PT. Arkonin (JO) | [5 empty] | 2. PT. Perentjana Djaja
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  |  |  | 3. PT. Gitarencana Multiplan
| 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku |  | Kardus 3 |  |  | 4. PT. Yodya Karya (Wilayah III Jakarta)
| 2. PT. Gitarencana Multiplan | [5 empty] | 5. PT. Supernova Jaya Mandiri
| 3. PT. Deta Decon | [5 empty] | 6. PT. Arkitek Team Empat
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  |  |  |  | Technical Proposal | 1. PT. Perentjana Djaja |  | 1 ori + 3 copy | Kontainer 13
| 5. PT. Arkitek Tema Empat | [5 empty] | 2. PT. Gitarencana Multiplan |  | 1 ori + 3 copy
| 6. PT. Griksa Cipta - PT. Arkonin (JO) | [5 empty] | 3. PT. Supernova Jaya Mandiri |  | 3 copy | Kontainer 14
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  |  |  | 4. Bina Karya |  | 1 ori + 3 copy
Technical Proposal | 1. PT. Widha - PT. Pola Data Konsultan (JO) | 4 buku | 1 copy | Kontainer 7
| PT. Widha - PT. Pola Data Konsultan (JO) | 4 buku | 2 copy | Kontainer 8
| 2. PT. Deta Decon | 3 buku | 1 ori + 2 copy | Kontainer 9
| 3. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku | 1 ori + 3 copy | Kontainer 10
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  | 1 ori + 1 copy
| PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  | 2 copy | Kontainer 11
| 5. PT. Gitarencana Multiplan |  | 1 ori + 3 copy
| 6. PT. Griksa Cipta - PT. Arkonin (JO) |  | 1 ori + 3 copy | Kontainer 12
| PT. Deta Decon | 3 buku | 1 copy | Kontainer 14
KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 1 | [5 empty] | PMSC PAKET 1
DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS
Technical Proposal | 1. Yodya Karya | 2 buku | 1 ori + 3 copy | Kontainer 1 |  | Technical Proposal | 1. PT. Artefak - PT. Disiplan (JO) |  | 3 copy | Kontainer 5
| 2. Virama Karya |  | 1 ori + 3 copy |  |  |  | 2. PT. Virama Karya (Persero) |  | 1 ori + 3 copy
| 3. Yaika Gama Utama - PT. Arkonin Engineering Manggala Pratama (JO) | 2 buku | 1 ori + 3 copy | Kontainer 2 |  |  | 3. PT.Patroon Arsindo - PT. Griksa Cipta (JO) |  | 1 ori + 3 copy
| 4. Gitarencana Multiplan |  | 1 ori + 3 copy | Kontainer 3 |  |  | 4. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) |  | 1 ori + 2 copy | Kontainer 6
| 5. Patroon Arsindo |  | 3 copy |  |  |  | 5. PT. Yodya Karya (Wilayah III Jakarta) |  | 1 ori + 3 copy
| 6. Artefak Arkindo - PT. Disiplan (JO) | 2 buku | 1 ori + 3 copy | Kontainer 4 |  |  | PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) |  | 1 copy | Kontainer 7
[7 empty] | PT. Patroon Arsindo - PT. Griksa Cipta (JO) |  | 1 ori + 1 copy
KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 2 | [5 empty] | PMSC PAKET 2
DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS
Technical Proposal | 1. PT. Artefak - PT. Disiplan (JO) |  | 3 copy | Kontainer 5 |  | Technical Proposal | 1. PT. Artefak Arkindo |  | 3 copy | Kontainer 18
| 2. PT. Virama Karya (Persero) |  | 1 ori + 3 copy |  |  |  | PT. Artefak Arkindo |  | 1 ori | Kontainer 19
| 3. PT.Patroon Arsindo - PT. Griksa Cipta (JO) |  | 1 ori + 3 copy |  |  |  | 2. PT. Deta Decon | 2 buku | 3 copy
| 4. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) |  | 1 ori + 2 copy | Kontainer 6 |  |  | 3. PT. Duta Hari Murthi Konsultan - PT. Arkonin EMP (JO) |  | 1 ori + 3 copy
| 5. PT. Yodya Karya (Wilayah III Jakarta) |  | 1 ori + 3 copy
| PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) |  | 1 copy | Kontainer 7
| PT. Patroon Arsindo - PT. Griksa Cipta (JO) |  | 1 ori + 1 copy
KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 3 | [5 empty] | PMSC PAKET 3
DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS
Technical Proposal | 1. PT. Widha - PT. Pola Data Konsultan (JO) | 4 buku | 1 copy | Kontainer 7 |  | Technical Proposal | 1. JV: PT. Cakra Manggilingan Jaya - PT. Adhicipta Engineering Consultant |  | 1 ori + 3 copy | Kontainer 16
| PT. Widha - PT. Pola Data Konsultan (JO) | 4 buku | 2 copy | Kontainer 8 |  |  | 2. JV: PT. Yodya Karya - PT. Gitarencana Multiplan |  | 1 ori + 3 copy | Kontainer 17
| 2. PT. Deta Decon | 3 buku | 1 ori + 2 copy | Kontainer 9 |  |  | 3. PT. Sangkuriang |  | 1 ori + 3 copy
| 3. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku | 1 ori + 3 copy | Kontainer 10 |  |  | 4. PT. Virama Karya | 2 buku | 1 ori + 3 copy | Kontainer 18
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  | 1 ori + 1 copy
| PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  | 2 copy | Kontainer 11
| 5. PT. Gitarencana Multiplan |  | 1 ori + 3 copy
| 6. PT. Griksa Cipta - PT. Arkonin (JO) |  | 1 ori + 3 copy | Kontainer 12
| PT. Deta Decon | 3 buku | 1 copy | Kontainer 14
KATALOG DOKUMEN PENGADAAN | [5 empty] | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 4 | [5 empty] | PMSC PAKET 4
DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan |  | KONTAINER/KARDUS
Technical Proposal | 1. PT. Perentjana Djaja |  | 1 ori + 3 copy | Kontainer 13 |  | Technical Proposal | 1. Al-Rajhi for Engineering Consultation |  | 1 ori + 4 copy | Kontainer 20
| 2. PT. Gitarencana Multiplan |  | 1 ori + 3 copy |  |  |  | 2. Alteraz Design |  | 1 ori + 4 copy
| 3. PT. Supernova Jaya Mandiri |  | 3 copy | Kontainer 14 |  |  | 3. PT. Deta Decon |  | 1 ori + 3 copy
| 4. Bina Karya |  | 1 ori + 3 copy |  |  |  | 4. PT. Kogas Driyap Konsultan |  | 3 copy
[7 empty] | 5. PT. Maxitech Utama Indonesia |  | 1 ori + 3 copy

## kataloglama
KATALOG DOKUMEN PENGADAAN |  |  |  |  | KATALOG DOKUMEN PENGADAAN |  |  |  |  | KATALOG DOKUMEN PENGADAAN |  |  |  | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 1 |  |  |  |  | DEDC PAKET 2 |  |  |  |  | PMSC PAKET 1 |  |  |  | PMSC PAKET 2
DOKUMEN | PERUSAHAAN | Keterangan | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan | KONTAINER/KARDUS | DOKUMEN | PERUSAHAAN | Keterangan | KONTAINER/KARDUS
Short-Listing Original | 1. PT. Patroon Arsindo |  | Kontainer 4 |  | Short-Listing Original | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku | Kontainer 3 |  |  | 1. PT. Artefak Arkindo, JO PT. Garis Rancang Bangun
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku |  |  |  | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 3. PT. Yodya Karya |  |  |  |  | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
| 4. PT. Darena Prakarsa Utama |  |  |  |  | 4. PT. Virama Karya (Persero)
| 5. PT. Gitarencana Multiplan |  |  |  |  | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 6. PT. Pandu Persada |  |  |  | Short-Listing Copy | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku | Kardus 7
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku |  |  |  | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 8. PT. Virama Karya (Pesero) |  |  |  |  | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
Short-Listing Copy | 1. PT. Patroon Arsindo |  | Kardus 10 |  |  | 4. PT. Virama Karya (Persero)
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku |  |  |  | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 3. PT. Yodya Karya |  |  |  |  | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku | Kardus 8
| 4. PT. Darena Prakarsa Utama |  |  |  |  | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 5. PT. Gitarencana Multiplan |  |  |  |  | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
| 6. PT. Pandu Persada |  |  |  |  | 4. PT. Virama Karya (Persero)
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku |  |  |  | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 8. PT. Virama Karya (Pesero) |  |  |  |  | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku | Kardus 9
| 1. PT. Patroon Arsindo |  | Kardus 11 |  |  | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku |  |  |  | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
| 3. PT. Yodya Karya |  |  |  |  | 4. PT. Virama Karya (Persero)
| 4. PT. Darena Prakarsa Utama |  |  |  |  | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 5. PT. Gitarencana Multiplan |  |  |  | Technical Proposal Original | 1. PT. Artefak - PT. Disiplan (JO) | 2 buku
| 6. PT. Pandu Persada |  |  |  |  | 2. PT. Yodya Karya (Wilayah III Jakarta)
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku |  | Yaika kurang buku 2 & 3 |  | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO)
| 8. PT. Virama Karya (Pesero) |  |  |  |  | 4. PT. Virama Karya (Persero)
| 1. PT. Patroon Arsindo |  | Kardus 12 |  |  | 5. PT.Patroon Arsindo - PT. Griksa Cipta (JO)
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku |  |  | Technical Proposal Copy | 1. PT.Patroon Arsindo - PT. Griksa Cipta (JO) | 3 copy | Kontainer 1
| 3. PT. Yodya Karya |  |  |  |  | 2. PT. Artefak - PT. Disiplan (JO) | 2 buku
| 4. PT. Darena Prakarsa Utama |  |  |  |  | 3. PT. Cakra Manggilingan Jaya - PT. Meridian Kreatama Mandiri (JO) | 3 copy
| 5. PT. Gitarencana Multiplan |  |  |  |  | 4. PT. Virama Karya (Persero)
| 6. PT. Pandu Persada |  |  |  |  | 4. PT. Virama Karya (Persero) | 2 copy | Kontainer 2
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku |  |  |  | 2. PT. Yodya Karya (Wilayah III Jakarta) | 2 copy |  | Yodya kurang 1
| 8. PT. Virama Karya (Pesero) |  |  |  |  | 2. PT. Artefak - PT. Disiplan (JO) | 2 buku ; 2 copy
Technical Proposal Original | 1. PT. Patroon Arsindo
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku
3. PT. Yodya Karya
4. PT. Darena Prakarsa Utama
5. PT. Gitarencana Multiplan
6. PT. Pandu Persada
| 7. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku
8. PT. Virama Karya (Pesero)
Technical Proposal Copy | 1. PT. Yodya Karya | 3 copy | Kontainer 1
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku
3. PT. Virama Karya (Pesero)
| 1. PT. Patroon Arsindo | 3 copy | Kontainer 2
| 2. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku
3. PT. Gitarencana Multiplan
| 4. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku
5. PT. Virama Karya (Pesero)
| 1. PT. Yaika Gema Utama - PT. Arkonin EMP (JO) | 2 buku ; 2 copy | Kontainer 3
| 2. PT. Gitarencana Multiplan | 2 copy
3. PT. Yodya Karya
| 4. PT. Artefak Arkindo - PT. Disolan (JO) | 2 buku
KATALOG DOKUMEN PENGADAAN |  |  |  |  | KATALOG DOKUMEN PENGADAAN
DEDC PAKET 3 |  |  |  |  | DEDC PAKET 4
DOKUMEN | PERUSAHAAN | Keterangan | KONTAINER/KARDUS |  | DOKUMEN | PERUSAHAAN | Keterangan | KONTAINER/KARDUS
Short-Listing Original | 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku | Kontainer 1 |  | Short-Listing Original | 1. PT. Kogas Driyap Konsultan |  | Kontainer 2
| 2. PT. Gitarencana Multiplan |  |  |  |  | 2. PT. Perentjana Djaja
| 3. PT. Deta Decon |  |  |  |  | 3. PT. Gitarencana Multiplan
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  |  |  |  | 4. PT. Yodya Karya (Wilayah III Jakarta)
| 5. PT. Arkitek Tema Empat |  |  |  |  | 5. PT. Supernova Jaya Mandiri
| 6. PT. Griksa Cipta - PT. Arkonin (JO) |  |  |  |  | 6. PT. Arkitek Team Empat
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  | Short-Listing Original | 1. PT. Kogas Driyap Konsultan |  | Kardus 4
Short-Listing Copy | 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku | Kardus 1 |  |  | 2. PT. Perentjana Djaja
| 2. PT. Gitarencana Multiplan |  |  |  |  | 3. PT. Gitarencana Multiplan
| 3. PT. Deta Decon |  |  |  |  | 4. PT. Yodya Karya (Wilayah III Jakarta)
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  |  |  |  | 5. PT. Supernova Jaya Mandiri
| 5. PT. Arkitek Tema Empat |  |  |  |  | 6. PT. Arkitek Team Empat
| 6. PT. Griksa Cipta - PT. Arkonin (JO) |  |  |  |  | 1. PT. Kogas Driyap Konsultan |  | Kardus 5
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  |  | 2. PT. Perentjana Djaja
| 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku | Kardus 2 |  |  | 3. PT. Gitarencana Multiplan
| 2. PT. Gitarencana Multiplan |  |  |  |  | 4. PT. Yodya Karya (Wilayah III Jakarta)
| 3. PT. Deta Decon |  |  |  |  | 5. PT. Supernova Jaya Mandiri
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  |  |  |  | 6. PT. Arkitek Team Empat
| 5. PT. Arkitek Tema Empat |  |  |  |  | 1. PT. Kogas Driyap Konsultan |  | Kardus 6
| 6. PT. Griksa Cipta - PT. Arkonin (JO) |  |  |  |  | 2. PT. Perentjana Djaja
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  |  | 3. PT. Gitarencana Multiplan
| 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku | Kardus 3 |  |  | 4. PT. Yodya Karya (Wilayah III Jakarta)
| 2. PT. Gitarencana Multiplan |  |  |  |  | 5. PT. Supernova Jaya Mandiri
| 3. PT. Deta Decon |  |  |  |  | 6. PT. Arkitek Team Empat
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  |  |  | Technical Proposal Original | 1. PT. Bina Karya, JO PT. Garis Rancang Bangun |  | Kontainer 1
| 5. PT. Arkitek Tema Empat |  |  |  |  | 2. PT. Gitarencana Multiplan
| 6. PT. Griksa Cipta - PT. Arkonin (JO) |  |  |  |  | 3. PT. Perentjana Djaja
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku |  |  |  | 4. PT. Supernova Jaya Mandiri
Technical Proposal Original | 1. PT. Widha - PT. Pola Data Konsultan (JO) | 2 buku |  |  | Technical Proposal Copy | 1. PT. Bina Karya, JO PT. Garis Rancang Bangun | 3 copy | Kontainer 2
| 2. PT. Gitarencana Multiplan |  |  |  |  | 2. PT. Gitarencana Multiplan
| 3. PT. Deta Decon |  |  |  |  | 3. PT. Perentjana Djaja
| 4. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) |  |  |  |  | 4. PT. Supernova Jaya Mandiri
5. PT. Arkitek Tema Empat
6. PT. Griksa Cipta - PT. Arkonin (JO)
| 7. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku
Technical Proposal Copy | 1. PT. Deta Decon | 3 buku | Kontainer 1
| 2. PT. Widha - PT. Pola Data Konsultan (JO) | 4 buku
| 3. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 buku
| 1. PT. Griksa Cipta - PT. Arkonin (JO) |  | Kontainer 2
| 2. PT. Gitarencana Multiplan | 2 copy
| 3. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO) | 2 copy
| 4. PT. Yodya Karya (Kantor Pusat) - PT. Duta Hari Murthi (JO) | 2 copy
| 1. PT. Deta Decon | 3 buku ; 2 copy | Kontainer 3
| 2. PT. Widha - PT. Pola Data Konsultan (JO) | 4 buku
| 1. PT. Griksa Cipta - PT. Arkonin (JO) | 2 copy | Kontainer 4
2. PT. Gitarencana Multiplan
3. PT. Virama Karya (Persero) Cab. Semarang - PT. Kogas (JO)
| 1. PT. Widha - PT. Pola Data Konsultan (JO) - ORIGINAL | 4 buku | Kontainer 5
| 2. PT. Widha - PT. Pola Data Konsultan (JO) - Copy | buku 1, 2 (2 copy), 3, 4